## 1-SL Exp & Rep
Location | Completion Date | Public Pipe Type | Prv. Exp. Pipe Type | Replacement Status
40-14-277-015 | 2020-05-20 | Copper | Lead | 02 3/4" PARTIAL REPLACEMENT, PRIVATE SIDE
40-14-277-016 | 2020-05-20 | Copper | Lead | 02 3/4" PARTIAL REPLACEMENT, PRIVATE SIDE
40-14-277-017 | 2020-05-20 | Copper | Lead | 02 3/4" PARTIAL REPLACEMENT, PRIVATE SIDE
46-35-327-023 | 2020-06-08 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
46-26-151-013 | 2020-06-08 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
46-35-130-001 | 2020-06-08 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
46-35-377-002 | 2020-06-08 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
46-26-205-006 | 2020-06-08 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
46-26-205-004 | 2020-06-08 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
46-26-205-019 | 2020-06-08 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
46-26-205-044 | 2020-06-08 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
46-35-154-032 | 2020-06-08 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
46-35-304-006 | 2020-06-08 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
46-35-304-003 | 2020-06-08 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
46-26-406-016 | 2020-06-08 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-30-104-032 | 2020-06-08 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
46-26-329-008 | 2020-06-08 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
46-35-353-006 | 2020-06-08 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
46-35-152-018 | 2020-06-08 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
46-25-204-006 | 2020-06-08 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
46-25-126-036 | 2020-06-08 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
46-35-153-028 | 2020-06-09 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-05-103-006 | 2020-06-09 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
46-26-205-014 | 2020-06-09 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-29-176-038 | 2020-06-09 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-29-181-035 | 2020-06-09 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-29-178-007 | 2020-06-09 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
46-35-430-029 | 2020-06-09 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
46-25-377-009 | 2020-06-09 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
46-35-232-011 | 2020-06-09 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
46-35-252-029 | 2020-06-09 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
46-35-253-004 | 2020-06-09 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-29-177-002 | 2020-06-09 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
46-25-434-011 | 2020-06-09 | Lead | Lead | 03 3/4" FULL REPLACEMENT
46-25-432-028 | 2020-06-09 | Lead | Copper | 01 3/4" PARTIAL REPLACEMENT, PUBLIC SIDE
47-29-177-027 | 2020-06-10 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-29-178-030 | 2020-06-10 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-29-226-036 | 2020-06-10 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-33-306-022 | 2020-06-10 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-33-304-020 | 2020-06-10 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
46-35-477-015 | 2020-06-10 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-33-377-015 | 2020-06-10 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-32-452-031 | 2020-06-10 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-30-230-009 | 2020-06-10 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-32-452-015 | 2020-06-10 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
46-25-227-002 | 2020-06-10 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
46-25-109-012 | 2020-06-10 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-30-408-025 | 2020-06-10 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-33-358-048 | 2020-06-11 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-33-357-005 | 2020-06-11 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-33-353-038 | 2020-06-11 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-29-176-040 | 2020-06-11 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-29-181-022 | 2020-06-11 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
46-36-128-003 | 2020-06-11 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-14-227-015 | 2020-06-11 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
47-33-352-025 | 2020-06-11 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-17-230-021 | 2020-06-12 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-04-177-032 | 2020-06-12 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-04-178-007 | 2020-06-12 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-04-177-036 | 2020-06-12 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-04-160-002 | 2020-06-12 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-04-428-014 | 2020-06-15 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
46-25-201-046 | 2020-06-15 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
46-25-202-002 | 2020-06-15 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
46-25-202-004 | 2020-06-15 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
46-25-226-055 | 2020-06-15 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-30-126-012 | 2020-06-15 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-33-376-110 | 2020-06-15 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-04-277-096 | 2020-06-15 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
46-25-201-039 | 2020-06-15 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-30-101-016 | 2020-06-15 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
47-30-101-023 | 2020-06-15 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
46-25-202-010 | 2020-06-16 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-04-330-018 | 2020-06-16 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
46-26-204-037 | 2020-06-16 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-23-203-019 | 2020-06-16 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
40-23-156-006 | 2020-06-16 | Copper | Copper | 03 3/4" FULL REPLACEMENT
40-23-154-013 | 2020-06-16 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
40-23-205-013 | 2020-06-16 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
46-25-202-009 | 2020-06-16 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-30-101-022 | 2020-06-16 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
41-17-102-013 | 2020-06-17 | Lead | Copper | 04 1" PARTIAL REPLACEMENT, PUBLIC SIDE
47-29-201-043 | 2020-06-17 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-29-201-045 | 2020-06-17 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-29-201-047 | 2020-06-17 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-29-202-001 | 2020-06-17 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-29-201-040 | 2020-06-17 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-29-201-042 | 2020-06-17 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-09-233-021 | 2020-06-17 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-08-451-019 | 2020-06-17 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-29-202-060 | 2020-06-17 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-11-480-010 | 2020-06-17 | Lead | Copper | 03 3/4" FULL REPLACEMENT
40-11-378-009 | 2020-06-17 | Lead | Copper | 03 3/4" FULL REPLACEMENT
47-29-102-007 | 2020-06-17 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-29-202-068 | 2020-06-17 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-09-211-004 | 2020-06-18 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-09-211-005 | 2020-06-18 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-04-452-025 | 2020-06-18 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-09-229-007 | 2020-06-18 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-09-205-004 | 2020-06-18 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-09-227-008 | 2020-06-18 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-09-205-002 | 2020-06-18 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
46-35-177-002 | 2020-06-18 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-09-209-004 | 2020-06-18 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-01-158-018 | 2020-06-18 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
40-14-462-016 | 2020-06-18 | Lead | Copper | 01 3/4" PARTIAL REPLACEMENT, PUBLIC SIDE
40-11-457-018 | 2020-06-18 | Galvanized | Galvanized | 03 3/4" FULL REPLACEMENT
46-26-227-028 | 2020-06-19 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
46-26-226-001 | 2020-06-19 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
46-35-382-017 | 2020-06-19 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-09-229-024 | 2020-06-19 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-02-105-037 | 2020-06-19 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
46-35-127-025 | 2020-06-19 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-11-230-018 | 2020-06-19 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
40-12-105-018 | 2020-06-19 | Lead | Copper | 01 3/4" PARTIAL REPLACEMENT, PUBLIC SIDE
40-02-180-010 | 2020-06-19 | Lead | Copper | 01 3/4" PARTIAL REPLACEMENT, PUBLIC SIDE
40-12-104-017 | 2020-06-19 | Galvanized | Galvanized | 03 3/4" FULL REPLACEMENT
40-02-108-017 | 2020-06-19 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
46-26-227-001 | 2020-06-19 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-32-228-026 | 2020-06-22 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-32-228-027 | 2020-06-22 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-02-132-036 | 2020-06-22 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-32-229-002 | 2020-06-22 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-32-229-026 | 2020-06-22 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-09-235-012 | 2020-06-22 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-03-477-011 | 2020-06-22 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-02-483-021 | 2020-06-22 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-11-254-030 | 2020-06-22 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-02-351-023 | 2020-06-22 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-02-309-032 | 2020-06-22 | Lead | Copper | 01 3/4" PARTIAL REPLACEMENT, PUBLIC SIDE
40-11-103-005 | 2020-06-22 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-03-484-002 | 2020-06-23 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-29-478-015 | 2020-06-23 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-29-478-016 | 2020-06-23 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-28-358-049 | 2020-06-23 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-28-355-068 | 2020-06-23 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-08-430-001 | 2020-06-23 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-11-456-014 | 2020-06-23 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-02-310-016 | 2020-06-23 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-02-404-045 | 2020-06-23 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-02-327-048 | 2020-06-23 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-08-410-006 | 2020-06-24 | Lead | Copper | 01 3/4" PARTIAL REPLACEMENT, PUBLIC SIDE
47-32-230-013 | 2020-06-24 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
46-26-126-044 | 2020-06-24 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-32-230-012 | 2020-06-24 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-32-229-013 | 2020-06-24 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-32-230-016 | 2020-06-24 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-12-253-024 | 2020-06-24 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
40-11-251-013 | 2020-06-24 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-02-376-005 | 2020-06-24 | Lead | Copper | 01 3/4" PARTIAL REPLACEMENT, PUBLIC SIDE
40-02-378-005 | 2020-06-24 | Lead | Copper | 01 3/4" PARTIAL REPLACEMENT, PUBLIC SIDE
40-02-327-014 | 2020-06-24 | Lead | Copper | 01 3/4" PARTIAL REPLACEMENT, PUBLIC SIDE
40-01-461-027 | 2020-06-24 | Galvanized | Lead | 03 3/4" FULL REPLACEMENT
40-11-201-002 | 2020-06-25 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
47-32-230-020 | 2020-06-25 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-32-230-019 | 2020-06-25 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-32-228-018 | 2020-06-25 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-11-276-009 | 2020-06-25 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
40-01-353-020 | 2020-06-25 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
40-11-226-003 | 2020-06-25 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
40-11-205-030 | 2020-06-25 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
40-02-455-015 | 2020-06-25 | Lead | Copper | 01 3/4" PARTIAL REPLACEMENT, PUBLIC SIDE
40-02-380-023 | 2020-06-25 | Copper | Lead | 03 3/4" FULL REPLACEMENT
40-12-106-018 | 2020-06-26 | Lead | Lead | 03 3/4" FULL REPLACEMENT
40-01-356-029 | 2020-06-26 | Lead | Copper | 01 3/4" PARTIAL REPLACEMENT, PUBLIC SIDE
40-02-379-007 | 2020-06-26 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
47-32-226-011 | 2020-06-26 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-02-234-009 | 2020-06-26 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
47-32-234-022 | 2020-06-26 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-33-104-045 | 2020-06-26 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-12-354-035 | 2020-06-26 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
41-16-428-021 | 2020-06-29 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-33-102-044 | 2020-06-29 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-33-357-039 | 2020-06-29 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-32-230-006 | 2020-06-29 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-32-230-009 | 2020-06-29 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-02-457-004 | 2020-06-29 | Galvanized | Copper | 01 3/4" PARTIAL REPLACEMENT, PUBLIC SIDE
40-01-305-014 | 2020-06-29 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-02-481-031 | 2020-06-29 | Lead | Copper | 01 3/4" PARTIAL REPLACEMENT, PUBLIC SIDE
41-05-276-002 | 2020-06-29 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-12-159-009 | 2020-06-30 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-11-480-008 | 2020-06-30 | Lead | Copper | 01 3/4" PARTIAL REPLACEMENT, PUBLIC SIDE
47-28-355-069 | 2020-06-30 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-11-352-019 | 2020-06-30 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-28-358-041 | 2020-06-30 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-28-358-042 | 2020-06-30 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-30-132-041 | 2020-06-30 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-12-159-014 | 2020-06-30 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-12-405-011 | 2020-06-30 | Lead | Lead | 03 3/4" FULL REPLACEMENT
40-02-458-006 | 2020-06-30 | Lead | Copper | 01 3/4" PARTIAL REPLACEMENT, PUBLIC SIDE
40-02-376-007 | 2020-06-30 | Galvanized | Copper | 04 1" PARTIAL REPLACEMENT, PUBLIC SIDE
47-32-235-001 | 2020-06-30 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-32-233-006 | 2020-06-30 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-19-384-007 | 2020-06-30 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-14-126-001 | 2020-06-30 | Lead | Copper | 01 3/4" PARTIAL REPLACEMENT, PUBLIC SIDE
40-14-202-002 | 2020-06-30 | Lead | Copper | 01 3/4" PARTIAL REPLACEMENT, PUBLIC SIDE
40-02-310-005 | 2020-06-30 | Lead | Copper | 01 3/4" PARTIAL REPLACEMENT, PUBLIC SIDE
40-01-456-026 | 2020-06-30 | Galvanized | Lead | 03 3/4" FULL REPLACEMENT
41-17-180-027 | 2020-07-01 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
46-25-155-015 | 2020-07-01 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-28-351-009 | 2020-07-01 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-28-301 zee-032 | 2020-07-01 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-14-307-022 | 2020-07-01 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-14-155-040 | 2020-07-01 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-29-477-005 | 2020-07-01 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-14-180-001 | 2020-07-01 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-04-103-026 | 2020-07-02 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-05-108-008 | 2020-07-02 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-12-353-037 | 2020-07-02 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
41-05-482-010 | 2020-07-06 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-05-482-012 | 2020-07-06 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-05-481-017 | 2020-07-06 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-12-257-019 | 2020-07-06 | Lead | Copper | 01 3/4" PARTIAL REPLACEMENT, PUBLIC SIDE
40-02-376-002 | 2020-07-06 | Lead | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-01-356-005 | 2020-07-06 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
40-14-160-015 | 2020-07-06 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
40-01-127-009 | 2020-07-06 | Lead | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-01-153-034 | 2020-07-06 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
40-01-455-004 | 2020-07-06 | Galvanized | Lead | 03 3/4" FULL REPLACEMENT
41-05-481-021 | 2020-07-07 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-11-480-028 | 2020-07-07 | Galvanized | Lead | 03 3/4" FULL REPLACEMENT
40-01-331-038 | 2020-07-07 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
46-35-303-006 | 2020-07-07 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-33-377-023 | 2020-07-07 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-01-104-010 | 2020-07-07 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-14-156-015 | 2020-07-07 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-02-376-009 | 2020-07-07 | Galvanized | Copper | 01 3/4" PARTIAL REPLACEMENT, PUBLIC SIDE
40-12-126-028 | 2020-07-08 | Galvanized | Lead | 03 3/4" FULL REPLACEMENT
47-33-377-013 | 2020-07-08 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-33-376-095 | 2020-07-08 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-33-376-068 | 2020-07-08 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-11-129-028 | 2020-07-08 | Galvanized | Lead | 03 3/4" FULL REPLACEMENT
40-01-456-015 | 2020-07-08 | Galvanized | Copper | 04 1" PARTIAL REPLACEMENT, PUBLIC SIDE
40-11-177-020 | 2020-07-08 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-17-153-017 | 2020-07-08 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
41-08-237-005 | 2020-07-08 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
40-14-202-006 | 2020-07-08 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
40-12-126-027 | 2020-07-08 | Galvanized | Copper | 04 1" PARTIAL REPLACEMENT, PUBLIC SIDE
40-14-177-019 | 2020-07-09 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-33-304-016 | 2020-07-09 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-33-304-014 | 2020-07-09 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-16-228-022 | 2020-07-09 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-10-233-006 | 2020-07-09 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-11-181-004 | 2020-07-09 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-33-351-050 | 2020-07-09 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
46-26-477-002 | 2020-07-09 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-11-108-017 | 2020-07-09 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-04-327-006 | 2020-07-09 | Galvanized | Lead | 03 3/4" FULL REPLACEMENT
40-01-230-004 | 2020-07-09 | Galvanized | Lead | 03 3/4" FULL REPLACEMENT
40-12-126-020 | 2020-07-09 | Lead | Copper | 01 3/4" PARTIAL REPLACEMENT, PUBLIC SIDE
40-10-231-032 | 2020-07-09 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-33-305-013 | 2020-07-09 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-23-153-002 | 2020-07-10 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-23-102-011 | 2020-07-10 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-29-477-016 | 2020-07-10 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-29-477-007 | 2020-07-10 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-17-180-022 | 2020-07-10 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-17-182-002 | 2020-07-10 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-17-182-004 | 2020-07-10 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-23-101-019 | 2020-07-10 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-17-129-030 | 2020-07-13 | Lead | Copper | 01 3/4" PARTIAL REPLACEMENT, PUBLIC SIDE
47-33-357-008 | 2020-07-13 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-33-357-020 | 2020-07-13 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-23-153-006 | 2020-07-13 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
47-28-301-025 | 2020-07-13 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-14-370-005 | 2020-07-13 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-14-462-022 | 2020-07-13 | Lead | Copper | 01 3/4" PARTIAL REPLACEMENT, PUBLIC SIDE
40-14-462-029 | 2020-07-13 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
40-14-366-021 | 2020-07-14 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-28-301-033 | 2020-07-14 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-28-301-017 | 2020-07-14 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-14-369-005 | 2020-07-14 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-14-462-039 | 2020-07-14 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
40-14-365-013 | 2020-07-14 | Lead | Copper | 01 3/4" PARTIAL REPLACEMENT, PUBLIC SIDE
40-14-463-022 | 2020-07-14 | Galvanized | Lead | 03 3/4" FULL REPLACEMENT
40-14-463-010 | 2020-07-14 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
40-14-463-006 | 2020-07-14 | Galvanized | Lead | 01 3/4" PARTIAL REPLACEMENT, PUBLIC SIDE
47-29-477-001 | 2020-07-15 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-28-351-020 | 2020-07-15 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-14-462-028 | 2020-07-15 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
47-33-104-046 | 2020-07-15 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-29-476-005 | 2020-07-15 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-28-358-032 | 2020-07-15 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-14-462-025 | 2020-07-15 | Lead | Copper | 01 3/4" PARTIAL REPLACEMENT, PUBLIC SIDE
40-14-484-015 | 2020-07-15 | Lead | Copper | 01 3/4" PARTIAL REPLACEMENT, PUBLIC SIDE
40-14-478-023 | 2020-07-15 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
47-32-234-014 | 2020-07-16 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-14-463-016 | 2020-07-17 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
47-33-101-012 | 2020-07-17 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-33-101-003 | 2020-07-17 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-14-384-009 | 2020-07-17 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-14-486-040 | 2020-07-17 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
47-28-351-006 | 2020-07-17 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-33-102-019 | 2020-07-17 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-14-463-007 | 2020-07-17 | Lead | Copper | 01 3/4" PARTIAL REPLACEMENT, PUBLIC SIDE
40-14-462-044 | 2020-07-17 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
40-14-484-005 | 2020-07-17 | Lead | Copper | 01 3/4" PARTIAL REPLACEMENT, PUBLIC SIDE
40-14-482-009 | 2020-07-20 | Lead | Copper | 01 3/4" PARTIAL REPLACEMENT, PUBLIC SIDE
41-04-106-017 | 2020-07-20 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-24-101-001 | 2020-07-20 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
47-32-454-025 | 2020-07-20 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-04-155-021 | 2020-07-20 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-14-387-014 | 2020-07-20 | Lead | Copper | 01 3/4" PARTIAL REPLACEMENT, PUBLIC SIDE
47-32-451-021 | 2020-07-20 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-14-389-006 | 2020-07-20 | Lead | Copper | 01 3/4" PARTIAL REPLACEMENT, PUBLIC SIDE
40-14-482-006 | 2020-07-20 | Lead | Copper | 01 3/4" PARTIAL REPLACEMENT, PUBLIC SIDE
40-14-462-030 | 2020-07-20 | Lead | Copper | 01 3/4" PARTIAL REPLACEMENT, PUBLIC SIDE
40-14-390-014 | 2020-07-20 | Lead | Copper | 01 3/4" PARTIAL REPLACEMENT, PUBLIC SIDE
40-14-390-013 | 2020-07-20 | Lead | Copper | 01 3/4" PARTIAL REPLACEMENT, PUBLIC SIDE
40-23-107-016 | 2020-07-21 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-04-178-013 | 2020-07-21 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-23-151-023 | 2020-07-21 | Lead | Copper | 01 3/4" PARTIAL REPLACEMENT, PUBLIC SIDE
40-23-207-005 | 2020-07-21 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-04-176-035 | 2020-07-21 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-23-231-012 | 2020-07-21 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-14-370-004 | 2020-07-21 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-23-110-018 | 2020-07-21 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-23-106-015 | 2020-07-21 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-28-355-078 | 2020-07-21 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-23-229-022 | 2020-07-21 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-14-463-017 | 2020-07-21 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-14-480-038 | 2020-07-21 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-14-487-006 | 2020-07-21 | Lead | Copper | 01 3/4" PARTIAL REPLACEMENT, PUBLIC SIDE
47-33-355-021 | 2020-07-22 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-28-351-013 | 2020-07-22 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-28-358-046 | 2020-07-22 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-28-351-011 | 2020-07-22 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-14-389-029 | 2020-07-22 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
40-14-389-040 | 2020-07-22 | Lead | Copper | 01 3/4" PARTIAL REPLACEMENT, PUBLIC SIDE
40-14-484-017 | 2020-07-22 | Lead | Copper | 01 3/4" PARTIAL REPLACEMENT, PUBLIC SIDE
40-14-484-016 | 2020-07-22 | Lead | Copper | 01 3/4" PARTIAL REPLACEMENT, PUBLIC SIDE
40-23-110-004 | 2020-07-23 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-23-131-045 | 2020-07-23 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-04-379-011 | 2020-07-23 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-23-133-039 | 2020-07-23 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-23-103-015 | 2020-07-23 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-14-462-007 | 2020-07-23 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-28-304-004 | 2020-07-23 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-33-102-039 | 2020-07-23 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-23-152-002 | 2020-07-23 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-23-152-017 | 2020-07-24 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-14-371-005 | 2020-07-24 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-23-103-013 | 2020-07-24 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-23-108-010 | 2020-07-24 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-33-104-022 | 2020-07-24 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-33-104-023 | 2020-07-24 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-33-104-024 | 2020-07-24 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-23-152-016 | 2020-07-24 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-23-108-003 | 2020-07-24 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-23-108-015 | 2020-07-24 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-23-230-010 | 2020-07-24 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-23-230-003 | 2020-07-24 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-14-458-020 | 2020-07-27 | Lead | Lead | 03 3/4" FULL REPLACEMENT
47-33-377-032 | 2020-07-27 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-04-106-003 | 2020-07-27 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-33-376-114 | 2020-07-27 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-33-376-060 | 2020-07-27 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-23-152-006 | 2020-07-27 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-23-229-004 | 2020-07-27 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-23-134-012 | 2020-07-27 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
40-23-126-014 | 2020-07-27 | Lead | Copper | 01 3/4" PARTIAL REPLACEMENT, PUBLIC SIDE
40-23-109-013 | 2020-07-27 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-23-133-014 | 2020-07-27 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
41-16-226-032 | 2020-07-28 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-23-208-001 | 2020-07-28 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
40-14-484-031 | 2020-07-28 | Lead | Copper | 01 3/4" PARTIAL REPLACEMENT, PUBLIC SIDE
40-14-456-010 | 2020-07-28 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
46-35-201-008 | 2020-07-28 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
41-05-352-019 | 2020-07-28 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
41-06-431-018 | 2020-07-28 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-23-102-029 | 2020-07-29 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-19-336-001 | 2020-07-29 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
46-36-406-018 | 2020-07-29 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-19-303-016 | 2020-07-29 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-04-432-020 | 2020-07-29 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-24-451-009 | 2020-07-29 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-24-431-008 | 2020-07-29 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-24-477-009 | 2020-07-29 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-05-105-011 | 2020-07-29 | Lead | Copper | 01 3/4" PARTIAL REPLACEMENT, PUBLIC SIDE
40-24-430-003 | 2020-07-29 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-19-376-020 | 2020-07-30 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-04-432-011 | 2020-07-30 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-33-103-018 | 2020-07-30 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-28-351-015 | 2020-07-30 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
47-28-351-018 | 2020-07-30 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-25-228-018 | 2020-07-30 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-25-231-002 | 2020-07-30 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-24-452-008 | 2020-07-30 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-25-226-011 | 2020-07-31 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-02-284-010 | 2020-07-31 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
41-16-455-035 | 2020-07-31 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-16-479-017 | 2020-07-31 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-19-305-017 | 2020-07-31 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-02-460-015 | 2020-07-31 | Galvanized | Lead | 03 3/4" FULL REPLACEMENT
40-25-226-010 | 2020-08-03 | Copper | Galvanized | 02 3/4" PARTIAL REPLACEMENT, PRIVATE SIDE
41-19-329-014 | 2020-08-03 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-14-326-013 | 2020-08-03 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-19-352-026 | 2020-08-03 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-24-476-009 | 2020-08-03 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-25-228-011 | 2020-08-04 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
41-16-403-025 | 2020-08-04 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-19-158-032 | 2020-08-04 | Lead | Copper | 01 3/4" PARTIAL REPLACEMENT, PUBLIC SIDE
41-16-477-079 | 2020-08-04 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-22-282-032 | 2020-08-04 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-16-479-018 | 2020-08-04 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-24-277-023 | 2020-08-05 | Lead | Copper | 01 3/4" PARTIAL REPLACEMENT, PUBLIC SIDE
41-16-402-019 | 2020-08-05 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-16-329-010 | 2020-08-05 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-22-233-005 | 2020-08-05 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-22-229-022 | 2020-08-05 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-22-228-035 | 2020-08-05 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-22-280-030 | 2020-08-05 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-22-284-015 | 2020-08-05 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-22-284-009 | 2020-08-05 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-22-282-018 | 2020-08-05 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-19-380-001 | 2020-08-05 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-12-107-029 | 2020-08-05 | Lead | Copper | 01 3/4" PARTIAL REPLACEMENT, PUBLIC SIDE
40-24-428-020 | 2020-08-05 | Lead | Copper | 01 3/4" PARTIAL REPLACEMENT, PUBLIC SIDE
40-22-233-006 | 2020-08-05 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-22-231-017 | 2020-08-05 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-19-356-027 | 2020-08-05 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-14-229-035 | 2020-08-05 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
40-23-154-025 | 2020-08-05 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
40-22-231-013 | 2020-08-05 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-22-283-001 | 2020-08-05 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
40-22-281-008 | 2020-08-06 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-22-279-017 | 2020-08-06 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-22-278-022 | 2020-08-06 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-22-278-008 | 2020-08-06 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-22-232-009 | 2020-08-06 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-16-477-026 | 2020-08-06 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-16-330-024 | 2020-08-06 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-22-232-028 | 2020-08-06 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-22-276-002 | 2020-08-06 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-22-276-013 | 2020-08-06 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-16-379-006 | 2020-08-06 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-22-228-013 | 2020-08-06 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-23-108-018 | 2020-08-06 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
40-22-232-034 | 2020-08-06 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-23-133-038 | 2020-08-07 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
40-22-279-012 | 2020-08-07 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-17-481-001 | 2020-08-07 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-22-229-016 | 2020-08-07 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-22-282-006 | 2020-08-07 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-22-283-008 | 2020-08-07 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-17-380-032 | 2020-08-07 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-17-477-017 | 2020-08-07 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-14-177-017 | 2020-08-07 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
46-35-155-019 | 2020-08-10 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-04-178-017 | 2020-08-10 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-29-278-023 | 2020-08-10 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-16-204-031 | 2020-08-10 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-04-206-012 | 2020-08-10 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-15-482-011 | 2020-08-10 | Copper | Galvanized | 02 3/4" PARTIAL REPLACEMENT, PRIVATE SIDE
40-15-483-003 | 2020-08-10 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-22-280-029 | 2020-08-10 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-22-281-016 | 2020-08-10 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-22-278-030 | 2020-08-10 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-22-278-025 | 2020-08-10 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-16-228-017 | 2020-08-10 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-15-456-007 | 2020-08-10 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-15-454-018 | 2020-08-10 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-15-458-006 | 2020-08-10 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-18-435-019 | 2020-08-10 | Copper | Lead | 05 1" PARTIAL REPLACEMENT, PRIVATE SIDE
40-22-276-031 | 2020-08-10 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-16-427-041 | 2020-08-11 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-16-426-012 | 2020-08-11 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-17-379-018 | 2020-08-11 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-29-257-042 | 2020-08-11 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-22-282-016 | 2020-08-11 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-15-454-015 | 2020-08-11 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-24-431-007 | 2020-08-11 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-15-456-006 | 2020-08-11 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-15-481-013 | 2020-08-11 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-15-486-005 | 2020-08-11 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-15-485-020 | 2020-08-11 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-22-231-021 | 2020-08-11 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-15-486-013 | 2020-08-11 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-16-228-009 | 2020-08-12 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-15-488-012 | 2020-08-12 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-04-452-006 | 2020-08-12 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-14-366-003 | 2020-08-12 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-23-109-029 | 2020-08-12 | Lead | Lead | 03 3/4" FULL REPLACEMENT
41-17-226-011 | 2020-08-12 | Copper | Lead | 02 3/4" PARTIAL REPLACEMENT, PRIVATE SIDE
41-17-381-022 | 2020-08-13 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-17-455-009 | 2020-08-13 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-20-404-040 | 2020-08-13 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-17-381-023 | 2020-08-13 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-29-254-027 | 2020-08-13 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-01-106-007 | 2020-08-13 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-25-176-020 | 2020-08-13 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-25-202-036 | 2020-08-13 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-17-403-010 | 2020-08-13 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-25-127-059 | 2020-08-13 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-23-182-018 | 2020-08-13 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-14-158-021 | 2020-08-13 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT
40-24-427-023 | 2020-08-14 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-09-209-011 | 2020-08-14 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-30-154-018 | 2020-08-14 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-30-159-026 | 2020-08-14 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-17-427-028 | 2020-08-14 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-17-429-013 | 2020-08-14 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-09-209-022 | 2020-08-14 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-25-276-033 | 2020-08-14 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
41-17-454-014 | 2020-08-14 | Copper | Copper | NO PORTION OF SERVICE LINE WAS REPLACED
40-12-129-026 | 2020-08-14 | Lead | Galvanized | 03 3/4" FULL REPLACEMENT

## 2-Filter Verification
Excavation Date | Address | Filter Verification Attempt 1 | Status - Attempt 1 | Filter Cartridge - Attempt 1 | Staff Comments - Attempt 1 | Filter Verification Attempt 2 | Status - Attempt 2 | Filter Cartridge - Attempt 2 | Staff Comments - Attempt 2 | Filter Verification Attempt 3 | Status - Attempt 3 | Filter Cartridge - Attempt 3 | Staff Comments - Attempt 3
2020-05-20 | DUPONT ST | 5/20/2020 3:11:10 PM | Resident Declined, Resident Already Installed Filter | Filter Cartridges Not Applicable
2020-05-20 | DUPONT ST | 5/20/2020 4:05:11 PM | Resident Declined, Resident Already Installed Filter | Filter Cartridges Provided
2020-06-09 | E GRACELAWN AVE | 6/9/2020 9:36:09 AM | Verification Complete, Filter Installed By Staff | Filter Cartridges Provided | Resident received Brita filters
2020-06-09 | ARIZONA AVE | 6/9/2020 12:52:44 PM | Verification Complete, Filter Installed By Staff
2020-06-09 | E GRACELAWN AVE | 6/9/2020 4:23:12 PM | Verification Complete, Filter Installed By Staff | Filter Cartridges Provided | Contractor entered house with COVID 19 protection.
2020-06-11 | N CHEVROLET AVE | 6/11/2020 9:00:00 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided | Brita filter unit
2020-06-15 | E CARPENTER RD | 6/15/2020 9:46:36 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Resident Not Home
2020-06-15 | E CARPENTER RD | 6/15/2020 12:18:57 PM | Verification Incomplete, Resident Not Home |  |  | 6/15/2020 5:15:00 PM | Verification Incomplete, Resident Not Home |  |  | 6/17/2020 10:23:00 AM | Verification Incomplete, Resident Not Home
2020-06-16 | BROWN ST | 6/16/2020 8:00:08 AM | Verification Complete, Filter Installed By Staff
2020-06-16 | BROWN ST | 6/16/2020 8:05:16 AM | Verification Complete, Filter Installed By Staff | Filter Cartridges Provided
2020-06-16 | CLAIRMONT ST | 6/16/2020 8:54:32 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided | Brita and PUR
2020-06-16 | CLAIRMONT ST | 6/16/2020 9:53:59 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided | Left Brita filter and unit on porch
2020-06-16 | E CARPENTER RD | 6/16/2020 11:05:05 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-06-17 | BAGLEY ST | 6/17/2020 8:10:24 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided | Brita filters supplied
2020-06-17 | TYRONE ST | 6/17/2020 8:09:59 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided | Brita filters supplied
2020-06-17 | WOODSIDE DR | 6/17/2020 8:00:00 AM | Resident Declined, Other (add staff comment) | Filter Cartridges Declined | Declined
2020-06-18 | W BAKER ST | 6/18/2020 8:30:00 AM | Verification Complete, Filter Installed By Staff
2020-06-18 | JOLIET ST | 6/18/2020 8:00:00 AM | Verification Incomplete, Other (add staff comment) | Resident Not Home | Home is vacant
2020-06-18 | GIBSON ST | 6/18/2020 11:00:23 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided | Brita
2020-06-19 | BEGOLE ST | 6/25/2020 10:41:05 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-06-19 | EUCLID AVE | 6/19/2020 9:20:19 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-06-19 | SEMINOLE ST | 6/19/2020 8:00:21 AM | Verification Complete, Filter Installed By Staff
2020-06-19 | LANDON ST | 6/19/2020 8:03:09 AM | Verification Incomplete, Other (add staff comment) | Filter Cartridges Provided | Resident wanted to install
2020-06-22 | WINONA ST | 6/22/2020 12:37:34 PM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided | Brita
2020-06-24 | LYON ST | 6/24/2020 1:23:30 PM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-06-24 | WINONA ST | 6/24/2020 4:19:15 PM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-06-24 | WELCH BLVD | 6/24/2020 10:28:05 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-06-24 | WELCH BLVD | 6/24/2020 10:35:48 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-06-24 | DONALD ST | 6/24/2020 4:00:00 PM | Verification Incomplete, Resident Not Home | Resident Not Home
2020-06-24 | S VERNON AVE | 6/23/2020 12:20:04 PM | Verification Incomplete, Resident Not Home | Resident Not Home |  | 6/23/2020 5:25:00 PM | Verification Incomplete, Resident Not Home |  |  | 6/24/2020 9:15:00 AM | Verification Incomplete, Other (add staff comment)
2020-06-25 | FOREST HILL AVE | 6/22/2020 12:06:43 PM | Resident Declined, Other (add staff comment) | Other (add staff comment) | Faucet not adaptable
2020-06-25 | BEGOLE ST | 6/25/2020 3:02:36 PM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided | Gave to resident.
2020-06-25 | JOSEPHINE ST | 6/25/2020 8:30:14 AM | Resident Declined, Other (add staff comment) | Filter Cartridges Declined
2020-06-25 | WELCH BLVD | 6/25/2020 11:28:45 AM | Resident Declined, Other (add staff comment) | Other (add staff comment) | Faucet not adaptable
2020-06-25 | FOREST HILL AVE | 6/25/2020 8:01:17 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-06-25 | MALLERY ST | 6/25/2020 10:44:53 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-06-25 | BARTH ST | 6/25/2020 10:31:18 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-06-26 | TUURI PL | 6/26/2020 3:21:41 PM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-06-26 | EUCLID AVE | 6/26/2020 11:27:56 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-06-26 | COPEMAN BLVD | 6/26/2020 7:46:00 AM | Resident Declined, Other (add staff comment) | Other (add staff comment) | Faucet not adaptable
2020-06-26 | W PATERSON ST | 6/26/2020 11:28:23 AM | Resident Declined, Alternative Water Filtration System | Filter Cartridges Declined
2020-06-26 | W MC CLELLAN ST | 6/26/2020 11:03:59 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-06-29 | STOCKDALE ST | 6/22/2020 7:50:41 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-06-29 | W PATERSON ST | 6/29/2020 12:00:00 PM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-06-30 | WELCH BLVD | 6/29/2020 3:54:42 PM | Resident Declined, Other (add staff comment) | Filter Cartridges Provided
2020-06-30 | WELCH BLVD | 6/29/2020 10:36:26 AM | Resident Declined, Other (add staff comment) | Filter Cartridges Declined
2020-06-30 | MARQUETTE ST | 6/30/2020 12:31:29 PM | Resident Declined, Other (add staff comment) | Other (add staff comment) | Faucet not adaptable
2020-06-30 | E PATERSON ST | 6/30/2020 3:00:00 PM | Resident Declined, Resident Already Installed Filter | Filter Cartridges Provided
2020-06-30 | SEVENTH AVE | 6/30/2020 2:13:20 PM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-06-30 | MONTEITH ST | 6/30/2020 8:03:46 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-06-30 | BAGLEY ST | 6/30/2020 12:14:43 PM | Verification Incomplete, Other (add staff comment) | Other (add staff comment) | Resident would not answer door
2020-06-30 | WELCH BLVD | 6/30/2020 3:00:00 PM | Resident Declined, Resident Already Installed Filter | Filter Cartridges Provided
2020-07-02 | EIGHTH AVE | 7/2/2020 9:45:13 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-07-06 | JOSEPHINE ST | 7/6/2020 8:53:11 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-07-06 | E WITHERBEE ST | 7/6/2020 6:00:00 PM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-07-06 | IROQUOIS AVE | 7/6/2020 7:57:16 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided | Brita
2020-07-06 | NORWOOD DR | 7/6/2020 8:01:39 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided | Left filters on porch
2020-07-06 | LYON ST | 7/6/2020 10:36:07 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-07-07 | W WITHERBEE ST | 7/7/2020 8:20:14 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-07-07 | PERRY ST | 11/20/2019 12:17:51 PM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-07-07 | WELCH BLVD | 7/7/2020 6:00:00 PM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-07-08 | WELCH BLVD | 7/8/2020 2:13:31 PM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Declined
2020-07-08 | WELCH BLVD | 7/8/2020 10:54:02 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-07-08 | E PATERSON ST | 7/7/2020 1:17:51 PM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-07-08 | KENNELWORTH AVE | 7/8/2020 7:49:33 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-07-08 | MONTEITH ST | 7/8/2020 8:17:34 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-07-08 | CLEMENT ST | 7/8/2020 3:43:10 PM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-07-08 | PENNSYLVANIA AVE | 7/8/2020 2:54:07 PM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-07-09 | DELAWARE AVE | 7/9/2020 3:39:34 PM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-07-09 | WELCH BLVD | 7/9/2020 8:27:31 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-07-09 | E JAMIESON ST | 7/9/2020 3:42:43 PM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-07-13 | S FRANKLIN AVE | 7/10/2020 12:31:39 PM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-07-13 | HERRICK ST | 7/13/2020 8:49:00 AM | Resident Declined, Other (add staff comment) | Filter Cartridges Declined
2020-07-13 | CORUNNA RD | 7/13/2020 9:12:45 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff
2020-07-13 | CORUNNA RD | 7/13/2020 3:39:26 PM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-07-14 | BARNEY AVE | 7/14/2020 2:42:44 PM | Verification Incomplete, Other (add staff comment) | Resident Not Home |  | 7/27/2020 8:51:56 AM | Resident Declined, Alternative Water Filtration System | Filter Cartridges Declined
2020-07-14 | CORUNNA RD | 7/14/2020 7:44:04 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-07-14 | CORUNNA RD | 7/14/2020 10:18:29 AM | Verification Complete, Filter Installed By Staff
2020-07-14 | CORUNNA RD | 7/14/2020 3:45:08 PM | Verification Incomplete, Other (add staff comment) | Filter Cartridges Not Applicable | Filter stock depleted; will return to residence once restocked | 8/10/2020 2:31:50 PM | Verification Incomplete, Resident Not Home | Resident Not Home
2020-07-14 | CORUNNA RD | 7/14/2020 7:21:22 PM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-07-15 | CORUNNA RD | 7/13/2020 8:07:08 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-07-15 | CORUNNA RD | 7/15/2020 8:17:21 AM | Verification Incomplete, Other (add staff comment) | Other (add staff comment) | Filter stock depleted; will return to residence once restocked | 7/27/2020 11:52:11 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-07-15 | CORUNNA RD | 7/15/2020 11:12:55 AM | Verification Incomplete, Other (add staff comment) | Other (add staff comment) | Filter stock depleted; will return to residence once restocked | 7/29/2020 9:36:53 AM | Verification Incomplete, Resident Not Home | Resident Not Home |  | 7/30/2020 6:30:00 PM | Resident Declined, Alternative Water Filtration System | Filter Cartridges Declined
2020-07-15 | CORUNNA RD | 7/15/2020 12:34:24 PM | Verification Incomplete, Other (add staff comment) | Other (add staff comment) | Filter stock depleted; will return to residence once restocked | 7/27/2020 11:36:24 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-07-17 | BRABYN AVE | 10/4/2019 9:57:40 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-07-17 | CORUNNA RD | 7/15/2020 8:05:10 AM | Verification Incomplete, Other (add staff comment) | Other (add staff comment) | Filter stock depleted; will return to residence once restocked | 8/7/2020 2:00:54 PM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-07-17 | CORUNNA RD | 7/16/2020 10:07:28 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Not Applicable | Filter stock depleted; will return to residence once restocked
2020-07-17 | CORUNNA RD | 7/17/2020 6:37:48 PM | Verification Incomplete, Other (add staff comment) | Other (add staff comment) | Filter stock depleted; will return to residence once restocked | 7/27/2020 11:53:15 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-07-17 | BROWN ST | 7/16/2020 9:54:32 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided | Brita filter unit
2020-07-20 | CORUNNA RD | 7/16/2020 6:00:00 PM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-07-20 | CORUNNA RD | 7/20/2020 11:43:54 AM | Verification Incomplete, Other (add staff comment) | Other (add staff comment) | Filter stock depleted; will return to residence once restocked | 7/27/2020 11:21:58 AM | Verification Incomplete, Resident Not Home | Resident Not Home |  | 7/27/2020 2:41:39 PM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-07-20 | CORUNNA RD | 7/20/2020 9:58:50 AM | Verification Incomplete, Other (add staff comment) | Other (add staff comment) | Filter stock depleted; will return to residence once restocked | 7/27/2020 11:26:53 AM | Verification Incomplete, Resident Not Home | Resident Not Home |  | 7/27/2020 2:42:42 PM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-07-20 | CORUNNA RD | 7/20/2020 4:57:17 PM | Verification Incomplete, Other (add staff comment) | Filter Cartridges Not Applicable | Filter stock depleted; will return to residence once restocked | 7/27/2020 12:43:54 PM | Verification Incomplete, Resident Not Home | Resident Not Home |  | 7/29/2020 9:29:48 AM | Resident Declined, Alternative Water Filtration System | Filter Cartridges Declined
2020-07-20 | CORUNNA RD | 7/20/2020 4:59:11 PM | Verification Incomplete, Other (add staff comment) | Filter Cartridges Not Applicable | Filter stock depleted; will return to residence once restocked | 7/27/2020 12:45:36 PM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-07-20 | REYNOLDS ST | 7/20/2020 10:54:10 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-07-20 | REYNOLDS ST | 7/20/2020 11:59:04 AM | Verification Incomplete, Other (add staff comment) | Other (add staff comment) | Filter stock depleted; will return to residence once restocked | 7/27/2020 2:12:17 PM | Resident Declined, Other (add staff comment) | Filter Cartridges Declined
2020-07-20 | DURAND ST | 7/27/2020 2:07:11 PM | Resident Declined, Other (add staff comment) | Filter Cartridges Declined
2020-07-21 | HERRICK ST | 7/21/2020 9:50:04 AM | Verification Incomplete, Other (add staff comment) | Filter Cartridges Not Applicable | Filter stock depleted; will return to residence once restocked | 7/27/2020 8:40:56 AM | Resident Declined, Other (add staff comment) | Filter Cartridges Declined
2020-07-21 | DURAND ST | 7/21/2020 11:06:20 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-07-22 | CORUNNA RD | 7/22/2020 11:43:39 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-07-22 | CORUNNA RD | 7/22/2020 8:30:34 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-07-22 | CORUNNA RD | 7/22/2020 10:29:31 AM | Resident Declined, Alternative Water Filtration System
2020-07-22 | CORUNNA RD | 7/22/2020 11:55:28 AM | Verification Incomplete, Other (add staff comment) | Other (add staff comment) | Filter stock depleted; will return to residence once restocked | 7/27/2020 11:35:10 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-07-27 | KNIGHT AVE | 7/27/2020 8:42:56 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-07-27 | REID ST | 7/27/2020 1:31:34 PM | Verification Incomplete, Resident Not Home | Resident Not Home | House being worked on. No water meter.
2020-07-27 | HUGHES AVE | 7/27/2020 2:30:03 PM | Resident Declined, Resident Already Installed Filter | Filter Cartridges Declined
2020-07-27 | BROWN ST | 7/27/2020 11:38:39 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-07-28 | CUMINGS AVE | 7/28/2020 3:31:43 PM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-07-28 | ZIMMERMAN ST | 7/28/2020 1:48:27 PM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-07-28 | BENNETT AVE | 7/28/2020 8:05:43 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-07-28 | SWAYZE ST | 7/28/2020 10:14:01 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-07-28 | FLEMING RD | 7/28/2020 3:36:03 PM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-07-29 | WYOMING AVE | 7/29/2020 8:00:29 AM | Verification Complete, Filter Installed By Staff
2020-07-31 | COPEMAN BLVD | 7/7/2020 5:48:00 PM | Verification Incomplete, Resident Not Home | Filter Cartridges Not Applicable | Resident was not home all day. | 7/8/2020 6:00:00 PM | Verification Incomplete, Resident Not Home | Filter Cartridges Not Applicable | Called numerous times with no answer | 8/10/2020 1:58:19 PM | Verification Incomplete, Resident Not Home | Resident Not Home
2020-07-31 | MT ELLIOTT AVE | 7/31/2020 1:38:47 PM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-08-03 | W ATHERTON RD | 8/3/2020 2:32:13 PM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-08-04 | CAMPBELL ST | 8/4/2020 8:35:00 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-08-04 | BRUNSWICK AVE | 8/4/2020 12:33:11 PM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-08-05 | SIMCOE AVE | 8/3/2020 9:28:55 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-08-05 | CARTIER ST | 8/3/2020 10:54:06 AM | Verification Incomplete, Other (add staff comment) | Filter Cartridges Not Applicable |  | 8/10/2020 2:06:52 PM | Verification Incomplete, Resident Not Home | Resident Not Home | Vacant home right now
2020-08-05 | NEOME DR | 8/5/2020 8:28:17 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-08-05 | REMINGTON AVE | 8/5/2020 8:22:31 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-08-05 | CLAIRMONT ST | 8/5/2020 9:37:33 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-08-05 | LARCHMONT ST | 8/5/2020 8:36:17 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided | PUR unit
2020-08-06 | MANN AVE | 7/23/2020 9:08:51 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-08-07 | CLANCY AVE | 8/10/2020 8:34:03 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-08-10 | BLACKINGTON AVE | 8/10/2020 5:09:51 PM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-08-10 | PARK ST | 8/10/2020 3:00:00 PM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-08-12 | E COURT ST | 8/12/2020 2:15:36 PM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-08-12 | STOCKER AVE | 8/12/2020 9:48:58 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-08-13 | VAN BUREN AVE | 8/13/2020 11:35:06 AM | Resident Declined, Other (add staff comment) | Filter Cartridges Declined | Filter will not fit on sink.
2020-08-14 | GARLAND ST | 8/14/2020 10:57:20 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided

## 3-Declinations
Address | Public Pipe Type | Prv. Exp. Pipe Type
ARIZONA AVE | Unknown | Unknown
DAVISON RD | Unknown | Unknown
DAVISON RD | Unknown | Unknown
DAVISON RD | Lead | Copper
DAVISON RD | Unknown | Unknown
IVANHOE AVE | Unknown | Unknown
IVANHOE AVE | Unknown | Unknown
KANSAS AVE | Unknown | Unknown
KENTUCKY AVE | Unknown | Unknown
KNAPMAN ST | Unknown | Unknown
LEVERN ST | Unknown | Unknown
LEWIS ST | Unknown | Unknown
NEBRASKA AVE | Unknown | Unknown
BROAD CT | Unknown | Unknown
BROAD CT | Unknown | Unknown
BROAD CT | Unknown | Unknown
CLIFFORD ST | Unknown | Unknown
CROOKED LN | Unknown | Unknown
S FRANKLIN AVE | Unknown | Unknown
HILLS ST | Unknown | Unknown
HOWARD AVE | Unknown | Unknown
W KEARSLEY ST | Unknown | Unknown
W KEARSLEY ST | Unknown | Unknown
KENSINGTON AVE | Unknown | Unknown
KENT ST | Unknown | Unknown
LIPPINCOTT BLVD | Unknown | Unknown
MAGNOLIA AVE | Unknown | Unknown
MASON ST | Unknown | Unknown
MARY ST | Unknown | Unknown
MASON ST | Unknown | Unknown
MASON ST | Unknown | Unknown
PARTRIDGE ST | Unknown | Unknown
PARTRIDGE ST | Unknown | Unknown
W PATERSON ST | Unknown | Unknown
PINGREE AVE | Unknown | Unknown
RIVERDALE RD | Unknown | Unknown
RIVERDALE RD | Unknown | Unknown
ROOT ST | Unknown | Unknown
S SAGINAW ST | Unknown | Unknown
W SECOND ST | Unknown | Unknown
W SECOND ST | Unknown | Unknown
W SECOND ST | Lead | Galvanized
SEVENTH AVE | Unknown | Unknown
STOCKDALE ST | Unknown | Unknown
W THIRTEENTH ST | Unknown | Unknown
W THIRTEENTH ST | Unknown | Unknown
W THIRTEENTH ST | Unknown | Unknown
E TWELFTH ST | Unknown | Unknown
WESTWOOD PKWY | Unknown | Unknown
WESTWOOD PKWY | Unknown | Unknown
WESTWOOD PKWY | Unknown | Unknown
W ATHERTON RD | Unknown | Unknown
BRUNSWICK AVE | Unknown | Unknown
CRAWFORD ST | Copper | Lead
DEARBORN ST | Unknown | Unknown
DELL AVE | Unknown | Unknown
ERIE ST | Unknown | Unknown
S GRAND TRAVERSE | Unknown | Unknown
GREENBROOK LN | Unknown | Unknown
GREENBROOK LN | Unknown | Unknown
GREENBROOK LN | Copper | Copper
LAUREL OAK DR | Unknown | Unknown
LAKEWOOD CT | Unknown | Unknown
LAKEWOOD CT | Unknown | Unknown
LAKEWOOD DR | Unknown | Unknown
LAKEWOOD DR | Unknown | Unknown
LINCOLN AVE | Unknown | Unknown
LINCOLN AVE | Copper | Copper
NEUBERT AVE | Unknown | Unknown
OGEMA AVE | Unknown | Unknown
PETTIBONE AVE | Unknown | Unknown
PEWANAGA PL | Unknown | Unknown
PEWANAGA PL | Copper | Copper
PEWANAGA PL | Unknown | Unknown
PINEHURST AVE | Unknown | Unknown
PINEHURST AVE | Unknown | Unknown
PINEHURST AVE | Unknown | Unknown
PINEHURST AVE | Unknown | Unknown
PINEHURST AVE | Unknown | Unknown
TIMBERLANE DR | Unknown | Unknown
TIMBERLANE DR | Unknown | Unknown
VICTORIA AVE | Unknown | Unknown
VICTORIA AVE | Unknown | Unknown
WALDMAN AVE | Unknown | Unknown
WALDMAN AVE | Unknown | Unknown
WALDMAN AVE | Unknown | Unknown
MARYLAND AVE | Unknown | Unknown
MARYLAND AVE | Unknown | Unknown
BRUNSWICK AVE | Unknown | Unknown
CRESTBROOK LN | Copper | Copper
CUTHBERTSON ST | Unknown | Unknown
NEUBERT AVE | Unknown | Unknown
VERMILYA AVE | Unknown | Unknown
CHELAN ST | Unknown | Unknown
LAUREL OAK DR | Unknown | Unknown
CORUNNA RD | Unknown | Unknown
MC PHAIL ST | Unknown | Unknown
SEYMOUR ST | Unknown | Unknown
WINDEMERE AVE | Unknown | Unknown
HERRICK ST | Unknown | Unknown
HUGHES AVE | Unknown | Unknown
LINCOLN AVE | Unknown | Unknown
BETA LN | Unknown | Unknown
EPSILON TR | Unknown | Unknown
WINSFORD BYWAY | Unknown | Unknown
AGREE AVE | Unknown | Unknown
SUNRIDGE DR | Copper | Copper
BRANCH RD | Unknown | Unknown
BINGHAM ST | Unknown | Unknown
BARBARA DR | Unknown | Unknown
ROSEANNA DR | Unknown | Unknown
ELMRIDGE DR | Unknown | Unknown
COMANCHE AVE | Unknown | Unknown
BRENT AVE | Unknown | Unknown
E CARPENTER RD | Unknown | Unknown
W CARPENTER RD | Unknown | Unknown
CASTLE LN | Unknown | Unknown
CHANDLER AVE | Unknown | Unknown
COMSTOCK AVE | Unknown | Unknown
CONCORD ST | Unknown | Unknown
COPEMAN BLVD | Unknown | Unknown
CRANWOOD DR | Unknown | Unknown
DAKOTA AVE | Unknown | Unknown
BEECHWOOD AVE | Unknown | Unknown
BEECHWOOD AVE | Unknown | Unknown
BEECHWOOD AVE | Unknown | Unknown
BEECHWOOD AVE | Unknown | Unknown
BENNETT AVE | Unknown | Unknown
BENNETT AVE | Unknown | Unknown
BENNETT AVE | Unknown | Unknown
BROADWAY BLVD | Unknown | Unknown
CAMDEN AVE | Unknown | Unknown
CHEROKEE AVE | Unknown | Unknown
CHEROKEE AVE | Unknown | Unknown
CUSTER AVE | Unknown | Unknown
CUTHBERTSON ST | Unknown | Unknown
DELL AVE | Unknown | Unknown
GOLD AVE | Unknown | Unknown
LAFAYETTE ST | Unknown | Unknown
W LAKEVIEW AVE | Unknown | Unknown
MACDONALD AVE | Unknown | Unknown
MACDONALD AVE | Unknown | Unknown
MACDONALD AVE | Unknown | Unknown
MACDONALD AVE | Unknown | Unknown
E MARENGO AVE | Unknown | Unknown
E NINTH ST | Unknown | Unknown
PENNSYLVANIA AVE | Unknown | Unknown
RED ARROW RD | Unknown | Unknown
RED ARROW RD | Unknown | Unknown
RED ARROW RD | Unknown | Unknown
WOODROW AVE | Unknown | Unknown
WOODROW AVE | Unknown | Unknown
WOODROW AVE | Unknown | Unknown
WOODROW AVE | Unknown | Unknown
WOODROW AVE | Unknown | Unknown
WOODROW AVE | Unknown | Unknown
ELMRIDGE DR | Unknown | Unknown
MACDONALD AVE | Unknown | Unknown
MACDONALD AVE | Unknown | Unknown
MENOMINEE AVE | Unknown | Unknown
RISEDORPH AVE | Unknown | Unknown
RISEDORPH AVE | Copper | Copper
RISEDORPH AVE | Unknown | Unknown
RISEDORPH AVE | Unknown | Unknown
SUNRIDGE DR | Unknown | Unknown
SUNRIDGE DR | Unknown | Unknown
SUNRIDGE DR | Unknown | Unknown
ALGONQUIN AVE | Unknown | Unknown
ALLENDALE PL | Unknown | Unknown
ALPHA WAY | Unknown | Unknown
ARIZONA AVE | Unknown | Unknown
AUGUSTA ST | Unknown | Unknown
S BALLENGER HWY | Unknown | Unknown
BARRIE AVE | Unknown | Unknown
BEAVER AVE | Unknown | Unknown
BEAVER AVE | Unknown | Unknown
PENGELLY RD | Unknown | Unknown
N CHEVROLET AVE | Unknown | Unknown
FOREST HILL AVE | Unknown | Unknown
FOREST HILL AVE | Unknown | Unknown
BAYBERRY LN | Unknown | Unknown
BERRYWOOD LN | Unknown | Unknown
BLACKINGTON AVE | Unknown | Unknown
BRANCH RD | Unknown | Unknown
BRANCH RD | Unknown | Unknown
BRENTWOOD DR | Unknown | Unknown
BROWN ST | Unknown | Unknown
BROWN ST | Unknown | Unknown
CALUMET ST | Unknown | Unknown
CALUMET ST | Unknown | Unknown
CAMPBELL ST | Unknown | Unknown
GREENBROOK LN | Unknown | Unknown
GREENBROOK LN | Unknown | Unknown
CHEYENNE AVE | Copper | Copper
CHEYENNE AVE | Unknown | Unknown
CHICAGO BLVD | Unknown | Unknown
LARCHMONT ST | Unknown | Unknown
LARCHMONT ST | Unknown | Unknown
COLCHESTER RD | Unknown | Unknown
E COURT ST | Unknown | Unknown
CRAIG DR | Unknown | Unknown
CUMINGS AVE | Unknown | Unknown
DARLING ST | Unknown | Unknown
DELAWARE AVE | Unknown | Unknown
DELAWARE AVE | Unknown | Unknown
DELAWARE AVE | Unknown | Unknown
N DEXTER ST | Unknown | Unknown
EASTHAMPTON DR | Unknown | Unknown
EASTHAMPTON DR | Unknown | Unknown
EATON PL | Unknown | Unknown
EATON PL | Unknown | Unknown
EDGEMONT AVE | Unknown | Unknown
EDGEMONT AVE | Unknown | Unknown
EPSILON TR | Unknown | Unknown
EPSILON TR | Unknown | Unknown
EPSILON TR | Copper | Copper
EVERGREEN PKWY | Unknown | Unknown
FENWICK CIR | Unknown | Unknown
FERNDALE PL | Unknown | Unknown
FIELDING ST | Unknown | Unknown
GAMMA LN | Unknown | Unknown
GAMMA LN | Unknown | Unknown
GLOUCESTER ST | Unknown | Unknown
GRATIOT AVE | Unknown | Unknown
GRATIOT AVE | Unknown | Unknown
HAMPSTEAD DR | Unknown | Unknown
HAMPSTEAD DR | Unknown | Unknown
HAMPSTEAD DR | Unknown | Unknown
HOGARTH AVE | Unknown | Unknown
HOLLY AVE | Unknown | Unknown
HOLLY AVE | Unknown | Unknown
HOLLY AVE | Unknown | Unknown
HOLLY AVE | Unknown | Unknown
HUGHES AVE | Unknown | Unknown
JOHNSON AVE | Unknown | Unknown
KEARSLEY PK BLVD | Unknown | Unknown
KNIGHT AVE | Unknown | Unknown
LAFAYETTE ST | Unknown | Unknown
LEITH ST | Unknown | Unknown
LEITH ST | Unknown | Unknown
LEXINGTON AVE | Unknown | Unknown
LEXINGTON AVE | Unknown | Unknown
LESTER ST | Unknown | Unknown
LEVERN ST | Copper | Copper
LORRAINE AVE | Unknown | Unknown
LOCHHEAD AVE | Unknown | Unknown
N LYNCH AVE | Unknown | Unknown
N LYNCH AVE | Unknown | Unknown
MANN AVE | Unknown | Unknown
MANN AVE | Unknown | Unknown
MANN AVE | Unknown | Unknown
MARGATE CIR | Unknown | Unknown
MARGATE CIR | Unknown | Unknown
MARYLAND AVE | Unknown | Unknown
MASON ST | Unknown | Unknown
MC KINLEY AVE | Unknown | Unknown
MISSOURI AVE | Unknown | Unknown
MOUNTAIN AVE | Unknown | Unknown
NEBRASKA AVE | Unknown | Unknown
CHATHAM DR | Unknown | Unknown
COLONIAL DR | Unknown | Unknown
COLONIAL DR | Unknown | Unknown
DUPONT ST | Unknown | Unknown
COLONIAL DR | Unknown | Unknown
E HEMPHILL RD | Unknown | Unknown
HUCKLEBERRY LN | Unknown | Unknown
W MARENGO AVE | Unknown | Unknown
NOLEN DR | Unknown | Unknown
NORBERT ST | Unknown | Unknown
NORBERT ST | Unknown | Unknown
W PASADENA AVE | Unknown | Unknown
E PIERSON RD | Unknown | Unknown
ROSELAWN DR | Unknown | Unknown
ROSELAWN DR | Unknown | Unknown
SALLY CT | Unknown | Copper
SENECA ST | Unknown | Unknown
SENECA ST | Unknown | Unknown
SOMERSET LN | Unknown | Unknown
STARKWEATHER ST | Unknown | Unknown
N STEVENSON ST | Unknown | Unknown
N STEVENSON ST | Unknown | Unknown
N STEVENSON ST | Unknown | Unknown
N STEVENSON ST | Unknown | Unknown
W STEWART AVE | Unknown | Unknown
W STEWART AVE | Unknown | Unknown
SUBURBAN CT | Unknown | Unknown
TIPTREE PATH | Copper | Copper
TWILIGHT DR | Unknown | Unknown
TWILIGHT DR | Unknown | Unknown
TWILIGHT DR | Unknown | Unknown
TWILIGHT DR | Unknown | Unknown
TWILIGHT DR | Unknown | Unknown
TWILIGHT DR | Copper | Copper
N BALLENGER HWY | Unknown | Unknown
BARNEY AVE | Unknown | Unknown
BEARD ST | Unknown | Unknown
BEGOLE ST | Unknown | Unknown
BELLE AVE | Unknown | Unknown
BERRYWOOD LN | Unknown | Unknown
BRABYN AVE | Unknown | Unknown
BRABYN AVE | Unknown | Unknown
BUCKINGHAM AVE | Unknown | Unknown
BUCKINGHAM AVE | Unknown | Unknown
CAMPBELL ST | Unknown | Unknown
CAMPBELL ST | Unknown | Unknown
CAMPBELL ST | Unknown | Unknown
CIRCLE DR | Unknown | Unknown
COPEMAN BLVD | Unknown | Unknown
COPEMAN BLVD | Unknown | Unknown
CRAWFORD ST | Unknown | Unknown
CRAWFORD ST | Unknown | Unknown
CRAWFORD ST | Unknown | Unknown
CRAWFORD ST | Unknown | Unknown
CRAWFORD ST | Unknown | Unknown
DEARBORN ST | Unknown | Unknown
DELAWARE AVE | Unknown | Unknown
E EIGHTH ST | Unknown | Unknown
S FRANKLIN AVE | Unknown | Unknown
BROADWAY BLVD | Unknown | Unknown
COLON ST | Unknown | Unknown
COMMONWEALTH AVE | Unknown | Unknown
COMMONWEALTH AVE | Unknown | Unknown
COMMONWEALTH AVE | Unknown | Unknown
S GRAND TRAVERSE | Unknown | Unknown
HARGOTT AVE | Unknown | Unknown
E HOLBROOK AVE | Unknown | Unknown
E HOLBROOK AVE | Unknown | Unknown
HUGHES AVE | Unknown | Unknown
HURON ST | Unknown | Unknown
INGLESIDE AVE | Unknown | Unknown
INGLESIDE AVE | Unknown | Unknown
KNIGHT AVE | Unknown | Unknown
LELAND ST | Unknown | Unknown
LETA AVE | Unknown | Unknown
LINCOLN AVE | Unknown | Unknown
LINCOLN AVE | Unknown | Unknown
LINCOLN AVE | Copper | Copper
S LYNCH AVE | Unknown | Unknown
MANN AVE | Unknown | Unknown
W MC CLELLAN ST | Unknown | Unknown
MC INTOSH DR | Unknown | Unknown
MISSOURI AVE | Unknown | Unknown
NEOME DR | Unknown | Unknown
SWAYZE ST | Unknown | Unknown
NORWOOD DR | Unknown | Unknown
OHIO AVE | Unknown | Unknown
OHIO AVE | Unknown | Unknown
ORR ST | Unknown | Unknown
OSSINGTON AVE | Unknown | Unknown
PENNSYLVANIA AVE | Unknown | Unknown
PENOYER CT | Unknown | Unknown
W PHILADELPHIA BLV | Unknown | Unknown
PINETREE DR | Unknown | Unknown
PROSPECT ST | Unknown | Unknown
PROSPECT ST | Unknown | Unknown
RED ARROW RD | Unknown | Unknown
RED ARROW RD | Unknown | Unknown
SALISBURY AVE | Unknown | Unknown
SHEFFIELD AVE | Unknown | Unknown
PLAINFIELD AVE | Unknown | Unknown
PLAINFIELD AVE | Unknown | Unknown
PLAINFIELD AVE | Unknown | Unknown
SUNDAY ST | Unknown | Unknown
WEAVER ST | Unknown | Unknown
WEAVER ST | Unknown | Unknown
WELCH BLVD | Unknown | Unknown
WELCH BLVD | Unknown | Unknown
WESTERN RD | Unknown | Unknown
WHITE ST | Unknown | Unknown
WHITNEY AVE | Unknown | Unknown
WHITNEY AVE | Unknown | Unknown
WHITNEY AVE | Unknown | Unknown
WHITTIER ST | Unknown | Unknown
WHITTIER ST | Unknown | Unknown
WINONA ST | Unknown | Unknown
WISNER ST | Unknown | Unknown
WOLCOTT ST | Unknown | Unknown
WOLCOTT ST | Unknown | Unknown
WOLCOTT ST | Unknown | Unknown
WOLCOTT ST | Unknown | Unknown
WOODCROFT AVE | Unknown | Unknown
WORCHESTER DR | Unknown | Unknown
WYOMING AVE | Unknown | Unknown
WYOMING AVE | Unknown | Unknown
ZIMMERMAN ST | Unknown | Unknown
LAUREL OAK DR | Unknown | Unknown
LAUREL OAK DR | Unknown | Unknown
LAUREL OAK DR | Unknown | Unknown
PENCOMBE PL | Unknown | Unknown
PENCOMBE PL | Unknown | Unknown
KANSAS AVE | Unknown | Unknown
W SEVENTH ST | Unknown | Unknown
ANN ARBOR ST | Unknown | Unknown
BAGLEY ST | Unknown | Unknown
N BALLENGER HWY | Unknown | Unknown
BERKLEY ST | Unknown | Unknown
CARTIER ST | Unknown | Unknown
CLOVERLAWN DR | Unknown | Unknown
COPEMAN BLVD | Unknown | Unknown
DICKINSON ST | Unknown | Unknown
DICKINSON ST | Unknown | Unknown
DUPONT ST | Unknown | Unknown
FLUSHING RD | Unknown | Unknown
FLUSHING RD | Unknown | Unknown
FRANK ST | Unknown | Unknown
FROST ST | Unknown | Unknown
MACKIN RD | Unknown | Unknown
MARQUETTE ST | Unknown | Unknown
MILBOURNE AVE | Unknown | Unknown
ORCHARD LN | Unknown | Unknown
ORCHARD LN | Unknown | Unknown
PERRY ST | Unknown | Unknown
RASKOB ST | Unknown | Unknown
RASKOB ST | Unknown | Unknown
TRUMBULL AVE | Unknown | Unknown
MANNHALL AVE | Unknown | Unknown
MARYLAND AVE | Unknown | Unknown
MARYLAND AVE | Unknown | Unknown
MILLER RD | Unknown | Unknown
MILLER RD | Unknown | Unknown
MONTERAY AVE | Unknown | Unknown
REYNOLDS ST | Unknown | Unknown
REYNOLDS ST | Unknown | Unknown
ROOSEVELT AVE | Unknown | Unknown
ROOSEVELT AVE | Unknown | Unknown
TACKEN ST | Unknown | Unknown
TACKEN ST | Unknown | Unknown
WILTON PL | Unknown | Unknown
WILTON PL | Unknown | Unknown
WILTON PL | Unknown | Unknown
BROAD CT | Unknown | Unknown
TORONTO ST | Unknown | Unknown
ADDISON ST | Unknown | Unknown
ADDISON ST | Unknown | Unknown
ADDISON ST | Unknown | Unknown
BALDWIN BLVD | Unknown | Unknown
W JAMIESON ST | Unknown | Unknown
M L KING AVE | Unknown | Unknown
M L KING AVE | Unknown | Unknown
MASON ST | Unknown | Unknown
W NEWALL ST | Unknown | Unknown
E PIERSON RD | Unknown | Unknown
W PIERSON RD | Unknown | Unknown
W STEWART AVE | Unknown | Unknown
E WITHERBEE ST | Copper | Copper
CLAIRMONT ST | Unknown | Unknown
W COURT ST | Unknown | Unknown
ZIMMERMAN ST | Unknown | Unknown
MILLER RD | Unknown | Unknown
BRADLEY AVE | Unknown | Unknown
BROWN ST | Unknown | Unknown
CHICAGO BLVD | Unknown | Unknown
CUMINGS AVE | Unknown | Unknown
CUMINGS AVE | Unknown | Unknown
CUMINGS AVE | Unknown | Unknown
FIELDING ST | Unknown | Unknown
FIELDING ST | Unknown | Unknown
GIBSON ST | Unknown | Unknown
GIBSON ST | Unknown | Unknown
HAMMOND ST | Unknown | Unknown
HUBBARD AVE | Unknown | Unknown
HUGHES AVE | Unknown | Unknown
KNAPP AVE | Unknown | Unknown
KNAPP AVE | Unknown | Unknown
KNIGHT AVE | Unknown | Unknown
KNIGHT AVE | Unknown | Unknown
REID ST | Unknown | Unknown
REID ST | Unknown | Unknown
REID ST | Unknown | Unknown
SUNSET DR | Unknown | Unknown
SWAYZE ST | Unknown | Unknown
SWAYZE ST | Unknown | Unknown
SWAYZE ST | Unknown | Unknown
SWAYZE ST | Unknown | Unknown
AUGUSTA ST | Unknown | Unknown
GRATIOT AVE | Unknown | Unknown
BEGOLE ST | Unknown | Unknown
W BELVIDERE AVE | Unknown | Unknown
BRIAR HILL RD | Unknown | Unknown
PARKSIDE DR | Unknown | Unknown
PARKSIDE DR | Unknown | Unknown
PARKSIDE DR | Unknown | Unknown
HAWTHORNE DR | Unknown | Unknown
HAWTHORNE DR | Copper | Copper
OVERHILL DR | Unknown | Unknown
ARLINGTON AVE | Unknown | Unknown
ARLINGTON AVE | Unknown | Unknown
JANE AVE | Unknown | Unknown
BROADWAY BLVD | Unknown | Unknown
BRANCH RD | Unknown | Unknown
COGGINS AVE | Unknown | Unknown