## Sheet1
Flint Water Infrastructure Funding
As of November 29, 2019
In early 2017, the U.S. Environmental Protection Agency awarded Water Infrastructure Improvements for the Nation (WIIN) grant funds of $100 million. In addition, the city of Flint (City) and State entered into a settlement agreement in late March 2017 to provide additional service line replacement funding. The following table summarizes the $167 million available for the City to address infrastructure needs. To date, 59% of the funds are remaining.
Category | Budget | Amount Approved for Reimbursement to City | Balance | Percent Remaining | Estimated Project Timeframe | Revised Project Time Frame
Federal WIIN Funds
Service line replacements | 20000000 | 7468430 | 12531570 | 62.66% | May 2017 - Dec 2019 | May 2017 - Dec 2019
Secondary water source | 9163300 | 338719 | 8824581 | 96.3% | Apr 2019 - Dec 2019 | Mar 2020 - Oct 2020
Dort and Cedar storage/pumping | 10125000 | 333155 | 9791845 | 96.71% | Apr 2019 - Mar 2020 | Dec 2019 - Dec 2020
Chemical feed building | 3400000 | 482953 | 2917047 | 85.8% | Mar 2019 - Dec 2019 | Mar 2020 - Dec 2020
Northwest transmission main | 12296900 | 324932 | 11971968 | 97.36% | Apr 2019 - Nov 2019 | Mar 2020 - Nov 2020
Water main replacement | 13683125 | 0 | 13683125 | 100% | Aug 2018 - TBD | Oct 2019 - Dec 2024
Meter replacement | 18460000 | 1933034 | 16526966 | 89.53% | Jan 2019 - Sep 2019 | Oct 2019 - Jun 2020
Water quality monitoring | 612500 | 127272 | 485228 | 79.22% | Jan 2019 - Mar 2019 | Oct 2019 - Oct 2020
Local assistance/capacity development | 2259175 | 1742230 | 516945 | 22.88% | May 2017 - Dec 2019 | May 2017 - Dec 2019
Service line replacement contingency | 10000000 | 0 | 10000000 | 100% | May 2017 - Dec 2019 | May 2017 - Dec 2019
Total Federal Funding | 100000000 | 12750725 | 87249275 | 87.25%
Other Funding
Service line replacement CHIP/DHHS | 10319659 | 10319659 | 0 | 0% |  | May 2017 - Sep 2019
Service line replacement State | 56700000 | 45282407 | 11417593 | 20.14% |  | May 2017 - Dec 2019
Total Other Funding | 67019659 | 55602066 | 11417593 | 17.04%
Total Water Infrastructure Funding | 167019659 | 68352791 | 98666868 | 59.08%
The City's FAST Start Team reports that 24,304 lines have been excavated and 9,448 lines replaced as of November 15, 2019, indicating a 38% replacment rate. An average cost per line will be calculated upon completion of work and reimbursment of invoices. EGLE recognizes there are outstanding invoices for work completed.
CHIP/DHHS funds were available in fiscal year (FY) 2017, FY 2018, and FY 2019. These funds lapse each year and as a result, the City was only able to utilize $10.3 million from this funding source. EGLE issued an amendment increasing the service line replacement grant by $7.7 million to account for the lapsed CHIP dollars. This amendment is illustrated in the "Service line replacement State" line above.