## Sheet1
Actual Finish | Address | Filter Verification Attempt 1 | Status - Attempt 1 | Filter Cartridge - Attempt 1 | Staff Comments - Attempt 1 | Filter Verification Attempt 2 | Status - Attempt 2 | Filter Cartridge - Attempt 2 | Staff Comments - Attempt 2 | Filter Verification Attempt 3 | Status - Attempt 3 | Filter Cartridge - Attempt 3 | Staff Comments - Attempt 3
2020-02-17 | E HAMILTON AVE | 2/17/2020 11:26:56 AM | Verification Complete, Filter Installed By Staff | Filter Cartridges Provided
2020-02-17 | E THIRD ST | 2/17/2020 2:00:00 PM | Verification Incomplete, Other (add staff comment) | Filter Cartridges Provided | Had 3 units in building. Provided filter and cartridges for all. Not installed because landlord was unsure if they were keeping existing sinks.
2020-02-17 | CADILLAC ST | 2/17/2020 9:57:29 AM | Verification Incomplete, Other (add staff comment) | Filter Cartridges Provided | Filter provided. House under going renovation and sink was not installed at this time.
2020-02-19 | JOLIET ST | 2/19/2020 10:14:22 AM | Verification Complete, Filter Installed By Staff | Filter Cartridges Provided
2020-02-19 | E THIRD ST | 2/17/2020 2:00:00 PM | Verification Incomplete, Other (add staff comment) | Filter Cartridges Provided | Had 3 units in building. Provided filter and cartridges for all. Not installed because landlord was unsure if they were keeping existing sinks.
2020-02-19 | DOUGHERTY PL | 2/19/2020 11:40:48 AM | Resident Declined, Other (add staff comment) | Filter Cartridges Declined | Filters don't fit on his sink |  | Resident Declined, Other (add staff comment) |  | Decline
2020-02-19 | CARTIER ST | 2/19/2020 10:16:17 AM | Resident Declined, Other (add staff comment) | Filter Cartridges Declined | Declined Filter |  | Verification Incomplete, Resident Not Home
2020-02-19 | OLIVE AVE | 2/19/2020 2:21:00 PM | Verification Complete, Filter Installed By Staff | Filter Cartridges Provided
2020-02-19 | DAMON ST | 2/19/2020 8:58:49 AM | Verification Complete, Filter Installed By Staff | Filter Cartridges Provided
2020-02-19 | DELAWARE AVE | 2/19/2020 5:11:25 PM | Verification Incomplete, Other (add staff comment) |  | Property is vacant.
2020-02-20 | COPEMAN BLVD | 2/20/2020 9:44:32 AM | Verification Complete, Filter Installed By Staff | Filter Cartridges Provided
2020-02-20 | COPEMAN BLVD | 2/20/2020 4:55:16 PM | Resident Declined, Resident Already Installed Filter | Filter Cartridges Provided
2020-02-20 | DAKOTA AVE | 2/20/2020 12:00:00 PM | Resident Declined, Other (add staff comment) |  | Filter would not fit on sink.
2020-02-20 | CARTIER ST | 2/20/2020 8:14:15 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided | Remodeling home sink not installed. Gave homeowner filter and cartridges
2020-02-20 | BURNS ST | 2/20/2020 4:15:00 PM | Verification Incomplete, Resident Not Home |  |  | 2/21/2020 1:00:00 PM | Verification Complete, Visual Confirmation of Filter Installation by Staff | Filter Cartridges Provided
2020-02-20 | E PIPER AVE | 2/20/2020 8:18:09 AM | Resident Declined, Resident Already Installed Filter | Filter Cartridges Provided
2020-02-20 | CADILLAC ST | 2/20/2020 10:37:39 AM | Verification Complete, Filter Installed By Staff | Filter Cartridges Provided
2020-02-21 | BUCKINGHAM AVE | 2/21/2020 1:50:57 PM | Verification Incomplete, Other (add staff comment) | Filter Cartridges Provided | Resident changing faucet and would install himself.
2020-02-21 | KEARSLEY PK BLVD | 2/21/2020 4:28:49 PM | Resident Declined, Other (add staff comment) | Filter Cartridges Declined | Filters would not fit sink.
2020-02-21 | COPEMAN BLVD | 2/21/2020 11:04:30 AM | Resident Declined, Resident Already Installed Filter | Filter Cartridges Provided | PUR filter installed, gave replacement cartridges to resident
2020-02-21 | BARTH ST | 2/21/2020 9:13:52 AM | Verification Complete, Filter Installed By Staff | Filter Cartridges Provided
2020-02-24 | BARTH ST | 2/24/2020 8:27:59 AM | Verification Complete, Filter Installed By Staff | Filter Cartridges Provided
2020-02-24 | BROADWAY BLVD | 2/24/2020 9:55:45 AM | Resident Declined, Resident Already Installed Filter | Filter Cartridges Provided
2020-02-24 | PENNSYLVANIA AVE | 2/24/2020 2:36:49 PM | Resident Declined, Resident Already Installed Filter | Filter Cartridges Declined
2020-02-24 | DAKOTA AVE | 2/24/2020 12:20:43 PM | Resident Declined, Other (add staff comment) | Other (add staff comment) | Home being remodeled. No one living in home, did not want at this time
2020-02-25 | COOK ST | 2/25/2020 11:15:25 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff
2020-02-25 | FERRIS AVE | 2/25/2020 10:12:57 AM | Verification Incomplete, Other (add staff comment) | Other (add staff comment) | Nobody answered door | 2/25/2020 12:47:10 PM | Verification Complete, Filter Installed By Staff | Filter Cartridges Provided
2020-03-02 | BARNEY AVE | 3/2/2020 8:23:54 AM | Verification Incomplete, Other (add staff comment) | Filter Cartridges Not Applicable | Filter would not fit sink.
2020-03-02 | LIPPINCOTT BLVD | 3/2/2020 4:08:46 PM | Resident Declined, Other (add staff comment) | Filter Cartridges Provided | Resident is redoing kitchen and has filter provided by the city.
2020-03-02 | MISSOURI AVE | 3/2/2020 4:55:42 PM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-03-03 | TACKEN ST | 3/3/2020 2:49:47 PM | Resident Declined, Alternative Water Filtration System
2020-03-03 | E JACKSON AVE | 3/3/2020 8:39:34 AM | Verification Complete, Filter Installed By Staff | Filter Cartridges Provided
2020-03-03 | COUNTRY CLUB LN | 3/3/2020 4:09:58 PM | Verification Complete, Filter Installed By Staff | Filter Cartridges Provided
2020-03-03 | FIELDING ST | 3/3/2020 11:09:33 AM | Verification Complete, Filter Installed By Staff | Filter Cartridges Provided
2020-03-04 | HAMMOND ST | 3/4/2020 11:34:37 AM | Verification Incomplete, Resident Not Home |  |  | 3/4/2020 5:35:24 PM | Verification Incomplete, Resident Not Home |  |  | 3/4/2020 10:20:53 AM | Verification Incomplete, Resident Not Home
2020-03-04 | MANNHALL AVE | 3/4/2020 9:02:01 AM | Verification Complete, Filter Installed By Staff
2020-03-04 | TACKEN ST | 3/4/2020 12:56:29 PM | Resident Declined, Other (add staff comment) |  | Remodeling, no sink installed in home
2020-03-04 | BENNETT CT | 3/4/2020 3:58:00 PM | Verification Complete, Filter Installed By Staff | Filter Cartridges Provided
2020-03-09 | PERRY ST | 3/9/2020 10:49:48 AM | Verification Complete, Filter Installed By Staff | Filter Cartridges Provided | Vacant
2020-03-09 | PROSPECT ST | 3/9/2020 12:08:33 PM | Resident Declined, Resident Already Installed Filter | Filter Cartridges Provided | Filter already installed, cartridge provided
2020-03-09 | THOM ST | 3/9/2020 11:48:20 AM | Resident Declined, Other (add staff comment) | Filter Cartridges Declined | Did not want filter.
2020-03-09 | LYON ST | 3/9/2020 4:57:38 PM | Verification Complete, Filter Installed By Staff | Filter Cartridges Provided
2020-03-10 | STOCKTON ST | 3/10/2020 11:48:00 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-03-10 | AVENUE B | 3/10/2020 2:05:45 PM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-03-11 | E RANKIN ST | 3/11/2020 10:44:15 AM | Verification Complete, Filter Installed By Staff | Filter Cartridges Provided
2020-03-11 | PARTRIDGE ST | 3/11/2020 8:41:19 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-03-11 | KENTUCKY AVE | 3/11/2020 1:39:21 PM | Resident Declined, Resident Already Installed Filter | Filter Cartridges Provided | Pur filter cartridges provided.
2020-03-11 | PENNSYLVANIA AVE | 3/11/2020 1:34:28 PM | Resident Declined, Resident Already Installed Filter | Filter Cartridges Provided | Pur filter cartridges provided.
2020-03-11 | COPEMAN BLVD | 3/11/2020 12:57:02 PM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided | Remodeling home, left filter and cartridges with homeowner. Did not want installed at this time
2020-03-17 | DUPONT ST | 3/17/2020 12:16:09 PM | Resident Declined, Resident Already Installed Filter | Filter Cartridges Provided | Filter already installed
2020-03-17 | DUPONT ST | 3/17/2020 8:35:15 AM | Verification Complete, Filter Installed By Staff | Filter Cartridges Provided
2020-03-17 | DUPONT ST | 3/17/2020 9:15:12 AM | Verification Complete, Filter Installed By Staff |  | Homeowner had no sink left filter and cartridges
2020-03-17 | DUPONT ST | 3/17/2020 9:32:19 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff |  | Did not want hooked up, left with homeowner
2020-03-25 | DELAWARE AVE | 3/25/2020 3:34:14 PM | Verification Complete, Filter Installed By Staff | Filter Cartridges Provided
2020-03-25 | BRANCH RD | 3/25/2020 3:59:42 PM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided | Provided filter to resident to install, resident installing filter
2020-03-27 | LOBDELL ST | 3/27/2020 8:48:58 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided | Provided homeowner with filter, homeowner to install
2020-05-20 | DUPONT ST | 5/20/2020 3:11:10 PM | Resident Declined, Resident Already Installed Filter | Filter Cartridges Not Applicable
2020-05-20 | DUPONT ST | 5/20/2020 3:37:49 PM | Verification Incomplete, Resident Not Home | Filter Cartridges Not Applicable | Home is for rent right now; and owner was not on-site during construction.
2020-05-20 | DUPONT ST | 5/20/2020 4:05:11 PM | Resident Declined, Resident Already Installed Filter | Filter Cartridges Provided
2020-06-09 | ARIZONA AVE | 6/9/2020 12:52:44 PM | Verification Complete, Filter Installed By Staff
2020-06-09 | E GRACELAWN AVE | 6/9/2020 9:36:09 AM | Verification Complete, Filter Installed By Staff | Filter Cartridges Provided | Resident received Brita filters
2020-06-09 | E GRACELAWN AVE | 6/9/2020 4:23:12 PM | Verification Complete, Filter Installed By Staff | Filter Cartridges Provided | Contractor entered house with COVID 19 protection.
2020-06-11 | N CHEVROLET AVE | 6/11/2020 9:00:00 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided | Brita filter unit
2020-06-15 | E CARPENTER RD | 6/15/2020 9:46:36 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Resident Not Home
2020-06-15 | E CARPENTER RD | 6/15/2020 12:18:57 PM | Verification Incomplete, Resident Not Home |  |  | 6/15/2020 5:15:00 PM | Verification Incomplete, Resident Not Home |  |  | 6/17/2020 10:23:47 AM | Verification Incomplete, Resident Not Home
2020-06-16 | BROWN ST | 6/16/2020 8:00:08 AM | Verification Complete, Filter Installed By Staff
2020-06-16 | CLAIRMONT ST | 6/16/2020 9:53:59 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided | Left Brita filter and unit on porch
2020-06-16 | CLAIRMONT ST | 6/16/2020 8:54:32 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided | Brita and PUR
2020-06-16 | E CARPENTER RD | 6/16/2020 11:05:05 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-06-16 | BROWN ST | 6/16/2020 8:05:16 AM | Verification Complete, Filter Installed By Staff | Filter Cartridges Provided
2020-06-17 | WOODSIDE DR | 6/17/2020 8:00:00 AM | Resident Declined, Other (add staff comment) | Filter Cartridges Declined | Declined
2020-06-17 | BAGLEY ST | 6/17/2020 8:10:24 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided | Brita filters supplied
2020-06-17 | TYRONE ST | 6/17/2020 8:09:59 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided | Brita filters supplied
2020-06-18 | W BAKER ST | 6/18/2020 8:30:00 AM | Verification Complete, Filter Installed By Staff
2020-06-18 | JOLIET ST | 6/18/2020 8:00:00 AM | Verification Incomplete, Other (add staff comment) | Resident Not Home | Home is vacant
2020-06-18 | GIBSON ST | 6/18/2020 11:00:23 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided | Brita
2020-06-19 | SEMINOLE ST | 6/19/2020 8:00:21 AM | Verification Complete, Filter Installed By Staff
2020-06-19 | LANDON ST | 6/19/2020 8:03:09 AM | Verification Incomplete, Other (add staff comment) | Filter Cartridges Provided | Resident wanted to install
2020-06-24 | DONALD ST | 6/24/2020 4:00:00 PM | Verification Incomplete, Resident Not Home | Resident Not Home
2020-06-24 | WELCH BLVD | 6/24/2020 10:35:48 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-06-24 | S VERNON AVE | 6/23/2020 12:20:04 PM | Verification Incomplete, Resident Not Home | Resident Not Home |  | 6/23/2020 5:25:04 PM | Verification Incomplete, Resident Not Home | Resident Not Home |  | 6/24/2020 9:15:36 AM | Verification Incomplete, Resident Not Home | Resident Not Home
2020-06-24 | WELCH BLVD | 6/24/2020 10:28:05 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-06-24 | LYON ST | 6/24/2020 1:23:30 PM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-06-24 | WINONA ST | 6/24/2020 4:19:15 PM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-06-25 | JOSEPHINE ST | 6/25/2020 8:30:14 AM | Resident Declined, Other (add staff comment) | Filter Cartridges Declined
2020-06-25 | WELCH BLVD | 6/25/2020 11:28:45 AM | Resident Declined, Other (add staff comment) | Other (add staff comment) | Faucet not adaptable
2020-06-25 | BARTH ST | 6/25/2020 10:31:18 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-06-25 | FOREST HILL AVE | 6/25/2020 8:01:17 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-06-25 | FOREST HILL AVE | 6/22/2020 12:06:43 PM | Resident Declined, Other (add staff comment) | Other (add staff comment) | Faucet not adaptable
2020-06-25 | MALLERY ST | 6/25/2020 10:44:53 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-06-29 | STOCKDALE ST | 6/22/2020 7:50:41 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-06-29 | W PATERSON ST | 6/29/2020 12:00:00 PM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-06-30 | E PATERSON ST | 6/30/2020 3:00:00 PM | Resident Declined, Resident Already Installed Filter | Filter Cartridges Provided
2020-06-30 | WELCH BLVD | 6/30/2020 3:00:00 PM | Resident Declined, Resident Already Installed Filter | Filter Cartridges Provided
2020-06-30 | MARQUETTE ST | 6/30/2020 12:31:29 PM | Resident Declined, Other (add staff comment) | Other (add staff comment) | Faucet not adaptable
2020-06-30 | BAGLEY ST | 6/30/2020 12:14:43 PM | Verification Incomplete, Other (add staff comment) | Other (add staff comment) | Resident would not answer door
2020-06-30 | SEVENTH AVE | 6/30/2020 2:13:20 PM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided
2020-06-30 | WELCH BLVD | 6/29/2020 3:54:42 PM | Resident Declined, Other (add staff comment) | Filter Cartridges Provided
2020-06-30 | WELCH BLVD | 6/29/2020 10:36:26 AM | Resident Declined, Other (add staff comment) | Filter Cartridges Declined
2020-06-30 | MONTEITH ST | 6/30/2020 8:03:46 AM | Verification Complete, Visual Confirmation of Filter Installation By Staff | Filter Cartridges Provided