## Sheet1
pid | 2/10 Lang-Rowe response | Clarification or documentation requested by Plaintiffs | 4/1 Rowe response
4012208004
4012282070
4012277038
4025127048
4025153058
4025101094
4025126031
4024380026 | Work completed 12/21/20 | Plaintiffs have not received a monthly excavation report for this date. Please provide complete documentation of this work, including the dates of excavation and replacement and the composition of the public and private side service line. | See 2020-04-01 NRDC Response Exploration Status
4119233014
4025101006
4025127037
4025101005
4025153019
4025127038
4025101095
4025101008
4012130045
4119330021
4025153046
4025101007
4015433010
4014177009
4023210012
4025153045
4025153053
4025101027
4023227013
4014361001
4012385032
4635379030
4025101013
4109231005
4025101028
4130106018
4635380008
4025101043
4025153049
4130106012
4025101011
4025101048
4025101036
4635458033
4120105009
4108433006
4025127039
4119403001
4023212004
4015456008
4109231006
4129155004
4730130022
4025127033
4011105014
4129180006
4024485019
4025127049
4015479009
4635359008
4117130016
4025101020
4104454021
4025101022
4002278011
4104454016
4024484018 | Never Assinged to Lang - WT has it as a decline | This address does not appear on the declination lists provided by the City. | The declintation was provided in the comments section by the contractor. The correct field was not toggled for it to appear in the Declination reporting. It has been corrected to appear in future reporting.
4001231015
4635358014
4014353021
4014486038
4129179020
4104454018
4119381024
4012278038 | Work Completed 12/22/20 | Plaintiffs have not received a monthly excavation report for this date. Please provide complete documentation of this work, including the dates of excavation and replacement and the composition of the public and private side service line. | See 2020-04-01 NRDC Response Exploration Status
4013106014
4636228075
4129151014
4129157013
4001231011
4129151048
4104456007
4025101019
4104454023
4015486011
4636153026
4130177025
4104454017
4130135024
4129180005
4108255043
4104454020
4129151033
4129151040
4105103016
4625152017
4001152035
4023155014
4104456003
4129157003
4119381025
4104456010
4730105017
4025153062
4733376112
4129151042
4011176003
4014180026
4116403033
4130226011
4012282065
4635104029
4635383036
4625433008
4635278026
4025101032
4626479033
4626480001
4014202003
4025201017
4733357010
4117230013
4120457053
4025153016
4025101047
4625154026
4015481016
4626476018
4635354009
4022276020
4635353024
4625280010
4108481013
4022276025
4012235019
4626427045
4130126024
4129254044
4625228007
4023107022
4635127008
4129104068
4014353012
4002108030
4105403006
4120455019
4025153020
4728355015 | Non Responsive - Mulitple attempts including after 5pm | Our analysis of the City's data showed that this address has not yet received the required in-person consent attempts, including at least one on weekend or after 5 PM. If the City has data showing that it has met the outreach requirements for this home, please provide that documentation. | According to CityWorks attempts were made: 10/15/2020 11:23 AM 10/21/2020 5:12 PM 10/19/2020 4:35 PM
4130129023
4635353015
4118285015
4012460007
4002108027
4129154025
4108482013
4626481005
4108429014
4023108023
4733355037
4733355044
4108479019
4635480015
4130159011
4022276011
4729176026
4729128014
4109234021 | Completed by Martha Brown | There is no record of this work on the monthly excavation reports. Please provide complete documentation of this work, including the dates of excavation and replacement and the composition of the public and private side service line. | Completed prior to this phase. According to records provided to Rowe, it was completed on 11/20/2018 and found to be copper to copper.
4120456012
4001481010
4635479029
4636179006
4015457007
4025101017
4014380017
4626480002
4116456029
4729127033
4635379015
4023108012
4022230027
4120476013
4120476008
4626329024
4635281022
4109234015
4130202012
4636377008
4635353023
4636178076
4626476007
4002109004
4108429022
4635127032
4120457025
4120453007
4024455032
4025153014
4119309005
4025202014
4109230015
4025226001
4120427009
4025203003
4002109027
4024455030
4001156018
4635129038
4626478022
4023158012
4001308002
4118280013
4121376029
4120426015
4119381023
4025201015
4635253012
4109479003
4120429029
4011183014
4625257010
4002234015
4117457023 | Have Ph# will attempt to schedule | Does this mean consent was received to perform an excavation at this address? | No physical consent form on file; resident contacted Rowe and provided their contact information.
4012277037
4108481014
4002154028
4635431002
4108431012
4626454020
4118436044
4116481020
4002126083
4002359018
4636179053
4116379015
4120404033
4120476004
4025201014
4117456017
4130133024
4635181003
4635128012
4635384040
4120457010
4732230015
4002232007
4120402049
4109231023
4025253030 | Work Completed 10/23/19 | There is no record of this work on the monthly excavation reports. Please provide complete documentation of this work, including the dates of excavation and replacement and the composition of the public and private side service line. | See 2020-04-01 NRDC Response Exploration Status
4626178011
4626401022
4626426002
4625151008
4014326003
4120429014
4733355042
4626176039
4108434005
4015477001
4625184015 | Cityworks has a 113 E Russel listed as Non-Responsive (multiple attempts including after 5pm) | Our analysis of the City's data showed that this address has not yet received the required in-person consent attempts, including at least one on weekend or after 5 PM. If the City has data showing that it has met the outreach requirements for this home, please provide that documentation. | According to CityWorks attempts were made for 113 E Russell: 04/25/2019 02/8/2020 10:42 AM 06/2/2020 2:13 PM 06/4/2020 6:50 PM
4129203012
4116329018
4002126002
4626426028
4011104016
4120428006
4120426007
4120404017
4117457019
4109235034
4129278034
4626429037
4625132021
4116202012
4012478001
4635155012
4108429017
4120402052
4635130010
4130129005
4120427012
4023126012
4002279015
4129154024
4635327010
4626429030
4011102003
4011329051
4014177028
4625434010
4117428010
4120404029
4109479001
4117476009
4012278010 | Work Completed 12/23/21 | Plaintiffs have not received a monthly excavation report for this date. Please provide complete documentation of this work, including the dates of excavation and replacement and the composition of the public and private side service line. | See 2020-04-01 NRDC Response Exploration Status
4025201047
4626177009
4117428008
4003476008
4109479002
4108453016
4014351014
4108433010
4120452025
4733104040
4117381019 | Work Completed 8/13/20 | There is no record of this work on the monthly excavation reports. Please provide complete documentation of this work, including the dates of excavation and replacement and the composition of the public and private side service line. | See 2020-04-01 NRDC Response Exploration Status
4625104001
4117427012
4120430007
4636129062
4108427011
4728357012
4626407043
4117427024
4002359028
4129226001
4109477005
4108478013
4011110022
4129104074
4117479013
4118284009
4002127002
4025280026 | Non-Responsive Multiple attempts made including after 5pm | Our analysis of the City's data showed that this address has not yet received the required in-person consent attempts, including at least one on weekend or after 5 PM. If the City has data showing that it has met the outreach requirements for this home, please provide that documentation. | According to CityWorks attempts were made: 04/25/2019 07/30/2019 2:57 PM 08/2/2019 5:00 PM
4002455010 | Non-Responsive Multiple attempts made including after 5pm | Our analysis of the City's data showed that this address has not yet received the required in-person consent attempts, including at least one on weekend or after 5 PM. If the City has data showing that it has met the outreach requirements for this home, please provide that documentation. | According to CityWorks attempts were made: 04/25/2019 06/18/2019 12:00 PM 09/9/2019 5:00 PM 06/12/2020 10:49 AM 06/15/2020 1:20 PM 06/18/2020 11:55 AM 06/25/2020 10:06 AM 06/29/2020 6:53 PM
4025203021
4120404027
4116428019
4729126034
4108479013
4129152030
4109210014
4117478009
4732234005
4729126037
4025101093
4012385030
4023210007
4129180012
4120430009
4025103003 | Work Completed 10/15/19 | There is no record of this work on the monthly excavation reports. Please provide complete documentation of this work, including the dates of excavation and replacement and the composition of the public and private side service line. | See 2020-04-01 NRDC Response Exploration Status
4625333005
4108479002
4625302004
4025102013 | Work Completed 10/16/19 | There is no record of this work on the monthly excavation reports. Please provide complete documentation of this work, including the dates of excavation and replacement and the composition of the public and private side service line. | See 2020-04-01 NRDC Response Exploration Status
4129154022
4117458028
4120402015
4729181002
4025106046
4011103002
4025104001 | Work completed 10/23/19 | There is no record of this work on the monthly excavation reports. Please provide complete documentation of this work, including the dates of excavation and replacement and the composition of the public and private side service line. | See 2020-04-01 NRDC Response Exploration Status
4635130029
4120404010
4002480024 | Non-Responsive Multiple attempts made including after 5pm | Our analysis of the City's data showed that this address has not yet received the required in-person consent attempts, including at least one on weekend or after 5 PM. If the City has data showing that it has met the outreach requirements for these homes, please provide that documentation. | According to CityWorks attempts were made: 04/25/2019 06/18/2019 12:00 PM 09/10/2019 2:00 PM 09/9/2019 5:00 PM 06/12/2020 10:40 AM 06/15/2020 1:25 PM 06/18/2020 06/25/2020 10:03 AM 06/29/2020 6:57 PM
4730379040
4120403024
4014177029
4025102011 | Work Completed 10/16/19 | There is no record of this work on the monthly excavation reports. Please provide complete documentation of this work, including the dates of excavation and replacement and the composition of the public and private side service line. | See 2020-04-01 NRDC Response Exploration Status
4116228028
4012255012
4116229016
4117231010
4116428033
4108429018
4626330035
4129152020
4025104019 | Work completed 10/23/19 | There is no record of this work on the monthly excavation reports. Please provide complete documentation of this work, including the dates of excavation and replacement and the composition of the public and private side service line. | See 2020-04-01 NRDC Response Exploration Status
4129151016
4012426035
4116452029
4625202022
4116452008
4120404026
4108433012
4003483007
4108432017
4108427042
4116226014
4010227010
4129205004 | Requires road closure - will schedule when we are able to open cut major rds | Does this mean consent was received to perform an excavation at this address? | No physical consent form on file; homeowner contacted Rowe and provided contact information to schedule.
4120456001
4002202009
4729479005
4729179007
4025105015 | Work Completed 10/9/19 | There is no record of this work on the monthly excavation reports. Please provide complete documentation of this work, including the dates of excavation and replacement and the composition of the public and private side service line. | See 2020-04-01 NRDC Response Exploration Status
4119306004
4130131024
4012277046 | Work Completed 12/23/20 | Plaintiffs have not received a monthly excavation report for this date. Please provide complete documentation of this work, including the dates of excavation and replacement and the composition of the public and private side service line. | See 2020-04-01 NRDC Response Exploration Status
4121326038
4012277044
4130133026
4011105015
4010228004
4116226013
4108376004
4626176035
4120456009
4120253011
4121326053
4023231028
4025102002 | Work Completed 10/16/19 | There is no record of this work on the monthly excavation reports. Please provide complete documentation of this work, including the dates of excavation and replacement and the composition of the public and private side service line. | See 2020-04-01 NRDC Response Exploration Status
4116427029
4626253005
4024455005
4025101010
4025106031 | Work completed 10/2/19 | There is no record of this work on the monthly excavation reports. Please provide complete documentation of this work, including the dates of excavation and replacement and the composition of the public and private side service line. | See 2020-04-01 NRDC Response Exploration Status
4120402018
4117479027
4012278004 | Work Completed 12/22/20 | Plaintiffs have not received a monthly excavation report for this date. Please provide complete documentation of this work, including the dates of excavation and replacement and the composition of the public and private side service line. | See 2020-04-01 NRDC Response Exploration Status
4012278033 | Work Completed 12/22/20 | Plaintiffs have not received a monthly excavation report for this date. Please provide complete documentation of this work, including the dates of excavation and replacement and the composition of the public and private side service line. | See 2020-04-01 NRDC Response Exploration Status
4014157031
4116226010
4012455005
4635152025
4117430042 | Work Completed 12/17/20 | Plaintiffs have not received a monthly excavation report for this date. Please provide complete documentation of this work, including the dates of excavation and replacement and the composition of the public and private side service line. | See 2020-04-01 NRDC Response Exploration Status
4025102001
4119130031
4116426009
4116228024
4014385001
4002206002
4025152006 | Work Completed 10/8/19 | There is no record of this work on the monthly excavation reports. Please provide complete documentation of this work, including the dates of excavation and replacement and the composition of the public and private side service line. | See 2020-04-01 NRDC Response Exploration Status
4116477042
4108432003
4626176015
4010202026
4025176032
4120402016
4024277015
4130153009
4002156011
4130127024
4025127004
4012476019
4121351020
4116203038
4117131026
4104178015
4729201010 | Have contact info - will attempt to schedule | Does this mean consent was received to perform an excavation at this address? | No physical consent form on file; resident contacted Lang and provided their contact information.
4129256046
4025176031
4025176024
4635177015
4104251009
4108455004
4022276033
4117429011
4109235041
4118228022
4104477032
4109426063
4120476026
4014307006
4120178024
4129276006
4120455010
4024378020
4729326007
4023403006
4734104009
4012231038
4012231037
4012231035
4012231036
4012231033
4023305072
4734103009
4025178078
4118226019
4107117043
4014103019
4012282067
4012282064
4012277045
4012207031
4012205015
4012209071